## Master App List (work) (hidden)
JCP&L Community Solar Pilot Project Interconnections
Interconnection Applications
Number | Date Application Received | Application ID or Utility Account # | Applicant Name | Site Address | City | Zip | Capacity (Max AC kW) | Date of Commercial Operation | Engineering Notes | Date of Approval to Install | Date of Approval to Operate | Notes:
1 | 2020-02-10 | QO19091024 | LW Solar NJ LLC | 120 Kenyon Dr | Lakewood | 8701 | 500 |  | 5704-Transmission Request | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
2 | 2020-02-10 | QO19091025 | IP Solar NJ LLC | 125 Kenyon Dr | Lakewood | 8701 | 500 |  | 5704-Transmission Request | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
3 | 2020-02-10 | QO19091026 | IP Solar NJ LLC | 945 Airport Rd | Lakewood | 8701 | 250 |  | Part 1 Approved on 4/7/2020 | 2020-04-07 |  | Application approved by BPU / Application received in JC_Interconnection
4 | 2020-02-10 | QO19091027 | LW Solar NJ LLC | 180 Lehigh Ave | Lakewood | 8701 | 550 |  | 5704-Transmission Request | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
5 | 2020-02-10 | QO19091028 | IP Solar NJ LLC | 1970 Rutgers Blvd | Lakewood | 8701 | 300 |  | 5704-Transmission Request | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
6 | 2020-02-10 | QO19091029 | IP Solar NJ LLC | 1915 Swarthmore Ave | Lakewood | 8701 | 250 |  | 5704-Transmission Request | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
7 | 2020-02-10 | QO19091030 | IP Solar NJ LLC | 150 N Oberlin Ave | Lakewood | 8701 | 750 |  | 5704-Transmission Request | 2020-07-09 |  | Application approved by BPU / Application received in JC_Interconnection
8 | 2020-02-10 | QO19091031 | LW Solar NJ LLC | 1955 Swarthmore Ave | Lakewood | 8701 | 400 |  | 5704-Transmission Request | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
9 | 2020-02-10 | QO19091032 | IP Solar NJ LLC | 170 N Oberlin Ave | Lakewood | 8701 | 850 |  | 5704-Transmission Request | 2020-07-09 |  | Application approved by BPU / Application received in JC_Interconnection
10 | 2020-02-14 | QO19091033 | LW Solar NJ LLC | 200 Lehigh Ave | Lakewood | 8701 | 400 |  | 5704-Transmission Request | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
11 | 2020-02-10 | QO19091035 | LW Solar NJ LLC | 750 Airport Rd | Lakewood | 8701 | 350 |  | Part 1 Approved on 4/7/2020 | 2020-04-07 |  | Application approved by BPU / Application received in JC_Interconnection
12 | 2020-02-04 | QO19091123 | CS Power Group LLC | 1957 Rutgers University Blvd | Lakewood | 8701 | 1100 |  |  | 2020-08-25 |  | Application approved by BPU / Application received in JC_Interconnection
13 | 2020-01-18 | QO19091124 | Citrine Power LLC (CP Franklin Solar, LLC c/o) | 674 Mountain View Rd East | Franklin | 8802 | 450 |  | Citrine power applied for 850 kW system. We initially gave them approval for a 450 kW system- which they were pursuing. Then at the same time they petitioned the NJBPU to put in a larger system- 1100 KW. The BPU approved their petition, and we then studied this increased amount and gave them a budgetary price to install it. Citrine indicated that the cost was too high for them and up to this point they have asked a few more questions but have not indicated what direction they want to go (450 kW or 1000 kW system). | 2020-08-21 |  | Application approved by BPU / Application received in JC_Interconnection
14 | 2020-02-07 | QO19091171 | NextGrid Inc (Manchester Township) | 1501 NJ-70 | Manchester Township | 8759 | 3200 |  | 5685-Transmission Request | 2020-07-13 |  | Application approved by BPU / Application received in JC_Interconnection
15 | 2020-02-25 | QO19091246 | Advance Solar Products | 1821 NJ-71 | Belmar | 7719 | 1750 |  | 10/23/2020 - Approval to Install send out…..8/14/20 - Pending TX review …..Submit to TX for review (TX5684) 3/30/20 | 2020-10-23 |  | Application approved by BPU / Application received in JC_Interconnection
16 | 2020-02-25 | QO19091248 | Spano Partners | 2498 Route 70 | Manchester Township | 8759 | 3586 |  | Transmission Request | 2020-10-19 |  | Application approved by BPU / Application received in JC_Interconnection
17 | 2019-10-30 |  | Phillipsburg Solar I, LLC | 6 Rand Blvd | Phillipsburg | 8865 | 4000 |  |  |  |  | Application NOT Approved by BPU / Application received in JC_Interconnection / DR # 344462937
18 | 2019-10-30 |  | Phillipsburg Solar II, LLC | 7 Rand Blvd | Phillipsburg | 8865 | 1500 |  |  |  |  | Application NOT Approved by BPU / Application received in JC_Interconnection / DR # 344463112
19 | 2020-02-04 | 100043092830 | Summer Wind Solar, LLC | 101 E. Quarry Rd | Oxford | 7863 | 4000 |  |  |  |  | Application NOT Approved by BPU / Application received in JC_Interconnection
20 | 2020-02-04 |  | Vesuvio Solar, LLC | Mountain Rd | Phohatcong | 8865 | 4000 |  |  |  |  | Application NOT Approved by BPU / Application received in JC_Interconnection / Nearest Pole # NJ561PT
21 | 2020-02-04 |  | Aldrin Solar, LLC | Blau Rd | Mansfield | 7840 | 4000 |  |  |  |  | Application NOT Approved by BPU / Application received in JC_Interconnection / Nearest Pole # NJ350MX
22 | 2020-02-04 |  | Pemberton CC, LLC | 105 Pole Bridge Rd | Brown Mills | 8015 | 3540 |  |  |  |  | Application NOT Approved by BPU / Application received in JC_Interconnection
23 | 2020-02-04 | 100135391348 | Broadway Energy | 2043 State Rt 57 | Washington | 7882 | 750 |  |  |  |  | Application NOT Approved by BPU / Application received in JC_Interconnection
24
25
26
27
28
29
30
Note on H4: Hosfelt, Sherri L: Maximum AC Rating
Note on M4: Hosfelt, Sherri L: Please make a note in this column of any data changes or anything special that needs noted.
Note on E14: Hosfelt, Sherri L: August 2020: Address change requested from 1989 Rutgers Blvd to 200 Lehigh Ave
Note on H17: Hosfelt, Sherri L: Per call with Vincent Scarmia and H Bakhtarwala, this should be 450 and not 850 kW
Note on K17: Hosfelt, Sherri L: This approval date is for the 450 kW system
Note on H19: Bakhtarwala, Hirendra H: 10/19/2020 Customer have increased the AC size from 1625kW to 1750kW

## Applications
JCP&L Community Solar Pilot Project Interconnections
Interconnection Applications
Number | Date Application Received | Application ID or Utility Account # | Applicant Name | Site Address | City | Zip | Capacity (Max AC kW) | Date of Approval to Install | Date of Commercial Operation | Notes:
1 | 2020-02-10 | QO19091024 | LW Solar NJ LLC | 120 Kenyon Dr | Lakewood | 8701 | 500 | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
2 | 2020-02-10 | QO19091025 | IP Solar NJ LLC | 125 Kenyon Dr | Lakewood | 8701 | 500 | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
3 | 2020-02-10 | QO19091026 | IP Solar NJ LLC | 945 Airport Rd | Lakewood | 8701 | 250 | 2020-04-07 |  | Application approved by BPU / Application received in JC_Interconnection
4 | 2020-02-10 | QO19091027 | LW Solar NJ LLC | 180 Lehigh Ave | Lakewood | 8701 | 550 | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
5 | 2020-02-10 | QO19091028 | IP Solar NJ LLC | 1970 Rutgers Blvd | Lakewood | 8701 | 300 | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
6 | 2020-02-10 | QO19091029 | IP Solar NJ LLC | 1915 Swarthmore Ave | Lakewood | 8701 | 250 | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
7 | 2020-02-10 | QO19091030 | IP Solar NJ LLC | 150 N Oberlin Ave | Lakewood | 8701 | 750 | 2020-07-09 |  | Application approved by BPU / Application received in JC_Interconnection
8 | 2020-02-10 | QO19091031 | LW Solar NJ LLC | 1955 Swarthmore Ave | Lakewood | 8701 | 400 | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
9 | 2020-02-10 | QO19091032 | IP Solar NJ LLC | 170 N Oberlin Ave | Lakewood | 8701 | 850 | 2020-07-09 |  | Application approved by BPU / Application received in JC_Interconnection
10 | 2020-02-14 | QO19091033 | LW Solar NJ LLC | 200 Lehigh Ave | Lakewood | 8701 | 400 | 2020-07-10 |  | Application approved by BPU / Application received in JC_Interconnection
11 | 2020-02-10 | QO19091035 | LW Solar NJ LLC | 750 Airport Rd | Lakewood | 8701 | 350 | 2020-04-07 |  | Application approved by BPU / Application received in JC_Interconnection
12 | 2020-02-04 | QO19091123 | CS Power Group LLC | 1957 Rutgers University Blvd | Lakewood | 8701 | 1100 | 2020-08-25 |  | Application approved by BPU / Application received in JC_Interconnection
13 | 2020-01-18 | QO19091124 | Citrine Power LLC (CP Franklin Solar, LLC c/o) | 674 Mountain View Rd East | Franklin | 8802 | 450 | 2020-08-21 |  | Application approved by BPU / Application received in JC_Interconnection
14 | 2020-02-07 | QO19091171 | NextGrid Inc (Manchester Township) | 1501 NJ-70 | Manchester Township | 8759 | 3200 | 2020-07-13 |  | Application approved by BPU / Application received in JC_Interconnection
15 | 2020-02-25 | QO19091246 | Advance Solar Products | 1821 NJ-71 | Belmar | 7719 | 1750 | 2020-10-23 |  | Application approved by BPU / Application received in JC_Interconnection
16 | 2020-02-25 | QO19091248 | Spano Partners | 2498 Route 70 | Manchester Township | 8759 | 3586 | 2020-10-19 |  | Application approved by BPU / Application received in JC_Interconnection
Note on H4: Hosfelt, Sherri L: Maximum AC Rating
Note on K4: Hosfelt, Sherri L: Please make a note in this column of any data changes or anything special that needs noted.

## Application Totals
JCP&L Community Solar Pilot Project Interconnections
Report Month & Cumulative Interconnection Application Totals
Report Month: | 2021-01-21
Number of Community Solar Interconnection Applications Received |  | 0
Number of Community Solar Facilities Interconnected |  | 0
Capacity (kW) of Community Solar Facilities Interconnected |  | 0
Estimated kWh Supplied to the Distribution System by Community Solar Facilities1
Number of Community Solar Subscribers
Estimated Community Solar Bill Credits Distributed to Community Solar Subscribers
Estimated "Excess" kWh
Cumulative Totals
Total Number of Community Solar Interconnection Applications Received |  | 16
Total Number of Community Solar Facilities Interconnected |  | 0
Total Capacity (kW) of Community Solar Facilities Interconnected |  | 0
Estimated Total kWh Supplied to the Distribution System by Community Solar Facilities1
Estimated Total Number of Community Solar Subscribers
Estimated Total Community Solar Bill Credits Distributed to Community Solar Subscribers
1Description of the Estimation Methodology: If actual data is not available, estimated data is based on actual data from the same time period the prior year, if available. Alternatively, data estimation is based on recent actual data.
Note on G18: Hosfelt, Sherri L: The estimated "excess" kilowatt hours are the estimated kilowatt hours produced by a community solar facility that were not allocated to a community solar subscriber