## Applications
Atlantic City Electric Company Community Solar Pilot Project Interconnections
Interconnection Applications (September 2021 Report)
Number | Date Application Received | Application ID or Utility Account # | Applicant Name | Site Address | City | Zip | Capacity (kW) | Date of Commercial Operation | Notes:
1 | 2020-01-16 |  | Nexamp Solar LLC | 1049 Fidler Hill Road (South) | Woodbine | 08270 | 4,999.02 (DC) 3,750 (AC) |  | The interconnection application was received on 01/16/2020 along with the site plan and one line diagram. Engineering began the technical review on 02/18/2020 and advised that the application and supporting documents were mislabeled. ACE reached out to the developer on 02/25/2020 and advised the developer that in order to proeed with technical review the application and supporting documents needed to be revised. ACE reached out to the developer (Nexamp LLC) and received the revisions. On 03/19/2020, a study letter was sent advising that a study will take approximately 60-90 days to complete. ACE received an email from Nexamp requesting a W9 form to remit payment for the cost of the study and application fees. ACE W9 form was emailed to Dallas Mason at Nexamp. The signed study letter was received back from Nexamp, LLC on 04/15/2020. On 5/5/2020, an invoice for the application fee was sent to the developer in the amount of $3,800. An invoice for $10,000 for the engineering study was issued 7/13/2020. Cost letter was issued on 10/9/2020. Alternative methods to avoid use of the transmission line path and potentially provide some cost savings were explored. Updated cost letter issued on 12/14/2020. Signed Document returned on 3/22/2021. Project has been initated. Countersignatures and project accounting being established. Invoices pending.
2 | 2020-01-16 |  | Nexamp Solar LLC | 1049 Fidler Hill Road (North) | Woodbine | 08270 | 4,451.46 (DC) 3,750 (AC) |  | The interconnection application was received on 01/16/2020 along with the site plan and one line diagram. Engineering began the technical review on 02/18/2020 and advised that the application and supporting documents were mislabeled. ACE reached out to the developer on 02/25/2020 and advised the developer that in order to proeed with technical review the application and supporting documents needed to be revised. ACE reached out to the developer (Nexamp LLC) and received the revisions. On 03/19/2020, a study letter was sent advising that a study will take approximately 60-90 days to complete. ACE received an email from Nexamp requesting a W9 form to remit payment for the cost of the study and application fees. ACE W9 form was emailed to Dallas Mason at Nexamp. The signed study letter was received back from Nexamp, LLC on 04/15/2020. On 5/5/2020, an invoice for the application fee was sent to the developer in the amount of $3,800. An invoice for $10,000 for the engineering study was issued 7/13/2020. Cost letter was issued on 10/9/2020. Alternative methods to avoid use of the transmission line path and potentially provide some cost savings were explored. Updated cost letter issued on 12/14/2020. Signed Document returned on 3/22/2021. Project has been initated. Countersignatures and project accounting being established. Invoices pending.
3 | 10/1/2020 (10/26/2020) - see notes |  | ACUA (Interconnection Application Not Received) | 6700 Delilah Road | Egg Harbor | 08234 | DC Not Reported 1,560 (AC) |  | Atlantic City Electric received a pilot program application, on 1/21/2020 ACE sent a letter of service territory verification to the developer. On 02/25/2020, ACE sent a followup email to the developer advising it to submit an ACE Community Solar interconnection application. As of 03/04/2020, ACE had not received the appriopiate interconnection application. On 03/17/20, ACE sent a follow up email requesting the developer to submit the appriopiate Community Solar application. ACE received a response from Greg Seher of ACUA on 03/18/202 stating. "They will be releasing their RFP for the project shortly and will select a vendor to complete the interconnection application." Interconnection application was sent via email on 10/1/2020; application was later submitted in the Connect to Grid website on 10/26/2020. Technical review identified need for an express feeder; awaiting feedback from ACUA on whether they wish to proceed. As of 6/1/2021 ACE is waiting for ACUA to determine whether they will move forward with the engineering interconnection study. ACE has held several meetings with ACUA and has recommended that ACUA move forward with the interconnection study.
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
Note on H4: Hosfelt, Sherri L: Maximum AC Rating
Note on J4: Hosfelt, Sherri L: Please make a note in this column of any data changes or anything special that needs noted.

## Application Totals
Atlantic City Electric Company Community Solar Pilot Project Interconnections
Report Month & Cumulative Interconnection Application Totals ( 2021) September
Report Month: | 2020-11-01
Number of Community Solar Interconnection Applications Received |  | 3
Number of Community Solar Facilities Interconnected |  | 0
Capacity (kW) of Community Solar Facilities Interconnected |  | 0
Estimated kWh Supplied to the Distribution System by Community Solar Facilities1 |  | 0
Number of Community Solar Subscribers |  | 0
Estimated Community Solar Bill Credits Distributed to Community Solar Subscribers |  | 0
Estimated "Excess" kWh |  | 0
Cumulative Totals
Total Number of Community Solar Interconnection Applications Received |  | 3
Total Number of Community Solar Facilities Interconnected |  | 0
Total Capacity (kW) of Community Solar Facilities Interconnected |  | 0
Estimated Total kWh Supplied to the Distribution System by Community Solar Facilities1 |  | 0
Estimated Total Number of Community Solar Subscribers |  | 0
Estimated Total Community Solar Bill Credits Distributed to Community Solar Subscribers |  | 0
1 Description of the Estimation Methodology: XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX
Note on G18: Hosfelt, Sherri L: The estimated "excess" kilowatt hours is the estimated kilowatt hours produced by a community solar facility that were not allocated to a community solar subscriber