## Table 1
Table 1 - Natural Gas
For Period Ending PY24Q2
Period Covered | Utility-Administered Retail Savings (DTh)1,2 | Comfort Partners Retail Savings (DTh) 1,2,5 | Other Programs Retail Savings (DTh)3 | Total Portfolio Retail Savings (DTh)1,2 | Compliance Baseline (DTh)4 | Annual Target (%) | Annual Target (DTh) | Percent of Annual Target (%)
| (A) | (B) | (C) | (D) = (A)+(B)+(C) | (E) | (F) | (G) = (E)*(F) | (H) = (D) / (G)
Quarter | 88564.1542 | 1066.2334 | N/A | 89630.3876
YTD | 133223.4695 | 1337.5896 | N/A | 134561.0591 | 50906112.3 | 0.51% | 259621.1727 | 51.83%
1 Calculated savings at the retail (customer meter) level. Savings are estimated from participation counts and TRM calculations, where applicable.
2 Encompasses all ex-ante savings for the Plan Year, including prior period adjustments.
3 Other Programs include Company-specific programs that are not part of the Clean Energy Act energy efficiency program and Comfort Partners, such as legacy programs and pilots.
4 Calculated as average annual gas usage in the prior three plan years (i.e., July – June) per N.J.S.A. 48:3-87.9(a). Details are provided in Appendix E.
⁵ NJ Comfort Partners savings is a preliminary estimate due to recently transitioning the data system of record, and subject to change based on further calculations. Savings true-up anticipated in future reporting periods.

## Table 2
Table 2 – Quantitative Performance Indicators | [8 empty] | For Period Ending PY24Q2 |  | Percent of Annual Target Achieved (Utility Administered Programs)
Natural Gas | Quarter |  |  |  | Year to Date | [5 empty] | Annual Energy Savings - Gas | Expenditures
| Utility-Administered Quarter Retail Savings | Comfort Partners Quarter Retail Savings⁴ | Other Programs Quarter Retail Savings | Total Portfolio Quarter Retail Savings | Utility-Administered YTD Retail Savings | Comfort Partners YTD Retail Savings⁴ | Other Programs YTD Retail Savings | Total Portfolio YTD Retail Savings | Annual Target1 | Percent of Annual Target Achieved | 51.71% | 33.31%
Annual Energy Savings (Dth) | 88564.1542 | 1066.2334 | N/A | 89630.3876 | 133223.4695 | 1337.5896 | N/A | 134561.0591 | 260231.1 | 51.71%
Lifetime Savings (Dth) | 690442.9236 | 16119.523 | N/A | 706562.4466 | 1208319.3021 | 20938.6269 | N/A | 1229257.929 | 2489059.6 | 49.39%
Annual Demand Savings (Dth Peak Day)
Low/Moderate-Income Lifetime Savings (Dth) 2 | 37800.14 | 16119.523 | N/A | 53919.663 | 95776.55 | 20938.6269 | N/A | 116715.1769
Small Commercial Lifetime Savings (Dth) 3 | 20905.1061 |  | N/A | 20905.1061 | 66446.0963 |  | N/A | 66446.0963
1 Annual targets reflect estimated impacts as filed in the Company’s EE filing
2 Low/Moderate-Income lifetime savings are provided separately for Comfort Partners and any income-qualified Residential or Multi-Family program.
3 Small Commercial lifetime savings are Direct Install program savings and those from C&I small business customers (<200 kW peak demand) in other programs.
⁴ NJ Comfort Partners savings is a preliminary estimate due to recently transitioning the data system of record, and subject to change based on further calculations. Savings true-up anticipated in future reporting periods.

## Tables 3-6
Table 3 – Sector-Level Participation
For Period Ending PY24Q2
Sector1 | Current Quarter Participants | YTD Participants | Annual Forecasted Participants | Percent of Annual Forecast
Residential | 171083 | 175747 | 193016 | 91.05%
Multi-Family | 129 | 314 | 1353 | 23.21%
C&I | 9 | 17 | 1164 | 1.46%
Reported Totals for Utility Administered Programs | 171221 | 176078 | 195533 | 90.05%
Comfort Partners | 184 | 291 | 4420 | N/A
Utility Total | 171405 | 176369 | 195533 | 90.2%
Table 4 – Sector-Level Expenditures
Expenditures1 | Current Quarter Expenditures ($000) | YTD Expenditures ($000) | Annual Budget Expenditures ($000) | Percent of Annual Budget
Residential | 6958.6747 | 13681.6209 | 38930.9327 | 35.14%
Multi-Family | 729.3482 | 857.0361 | 3129.6223 | 27.38%
C&I | 533.0556 | 1583.4736 | 6333.994 | 25%
Reported Totals for Utility Administered Programs | 8221.0785 | 16122.1307 | 48394.5489 | 33.31%
Comfort Partners | 1609.22 | 2228.0583 | 4289.861 | 51.94%
Utility Total | 9830.2985 | 18350.1891 | 48394.5489 | 37.92%
Table 5 – Sector-Level Energy Savings
Annual Energy Savings1 | Quarter Retail (Dth) | YTD Retail (Dth) | Annual Target Retail Savings (Dth) | Percent of Annual Target
Residential | 83501.0442 | 124197.0817 | 236270.6 | 52.57%
Multi-Family | 3033.8443 | 4139.2753 | 4276.8 | 96.78%
C&I | 2029.2657 | 4887.1125 | 19683.7 | 24.83%
Reported Totals for Utility Administered Programs | 88564.1542 | 133223.4695 | 260231.1 | 51.19%
Comfort Partners | 1066.2334 | 1337.5896 | 25527 | N/A
Utility Total | 89630.3876 | 134561.0591 | 260231.1 | 51.71%
Table 6 – Annual Costs and Budget Variances by Category
Total Utility EE/PDR | Quarter Reported ($000) | YTD Reported ($000) | Full Year Budget ($000) | Percent of Annual Budget Spent
Capital Costs | 0 | 0 | 0 | N/A
Utility Administration | 393.907 | 666.6176 | 1749.403 | 38.11%
Marketing | 157.1135 | 227.6239 | 1108.076 | 20.54%
Outside Services | 404.6243 | 746.3581 | 5260.874 | 14.19%
Rebates | 3416.3811 | 6695.1583 | 19569.813 | 34.21%
No- or Low-Interest Loans | 3697.5929 | 7497.2985 | 18777.891 | 39.93%
Evaluation, Measurement & Verification ("EM&V") | 104.7984 | 233.9627 | 1592.17 | 14.69%
Inspections & Quality Control | 46.6699 | 55.1077 | 336.323 | 16.39%
Utility EE/PDR Total | 8221.0871 | 16122.1268 | 48394.55 | 33.31%

## Table 7
Table 7 – Equity Performance
For Period Ending PY24Q2
Territory-Level Benchmarks | Overburdened1 | Non-Overburdened | %OBC2
# of Household Accounts3 | 75092 | 294981 | 20.29%
# of Business Accounts3 | 8655 | 18467 | 31.91%
Total Annual Energy (Dth)4 | 13315218 | 25643619 | 34.18%
Programs | Sub Program or Offering | Types of Sub Program Offering | Quarter Overburdened1 | Quarter Non-Overburdened | % OBC2 | YTD Overburdened | YTD Non-Overburdened | % OBC2
Participation
Residential - Efficient Products | HVAC | Core | 157 | 1239 | 11.25% | 354 | 2655 | 11.76%
| Appliance Rebates | Core | 68 | 448 | 13.18% | 124 | 852 | 12.7%
| Online Marketplace | Core | 826 | 4011 | 17.08% | 1222 | 5920 | 17.11%
| EE Giveaway Kits | Core | 0 | 1 | 0% | 0 | 1 | 0%
Residential - Existing Homes | Home Performance with Energy Star | Core | 3 | 32 | 8.571% | 3 | 54 | 5.263%
| Quick Home Energy Checkup | Additional | 32 | 159 | 16.75% | 71 | 224 | 24.07%
| Moderate Income Weatherization | Additional | 20 | 67 | 22.99% | 40 | 207 | 16.19%
Behavioral | Behavioral | Additional | 24555 | 139465 | 14.97% | 24555 | 139465 | 14.97%
C&I Direct Install | Direct Install | Core | 1 | 1 | 50% | 6 | 3 | 66.67%
Energy Solutions for Business | Prescriptive/Custom | Core | 4 | 3 | 57.14% | 4 | 4 | 50%
| Energy Management | Additional | 0 | 0 | N/A | 0 | 0 | N/A
| Engineered Solutions | Additional | 0 | 0 | N/A | 0 | 0 | N/A
Multi-Family | Multi-Family Home Performance with Energy Star | Core | 0 | 2 | 0% | 0 | 2 | 0%
| Multi-Family Direct Install | Core | 0 | 80 | 0% | 5 | 259 | 1.894%
| Multi-Family Prescriptive / Custom | Core | 0 | 0 | N/A | 1 | 0 | 100%
| Multi-Family Engineered Solutions | Core | 0 | 1 | 0% | 0 | 1 | 0%
Total Core Participation |  |  | 1059 | 5818 | 15.4% | 1719 | 9751 | 14.99%
Total Additional Participation |  |  | 24607 | 139691 | 14.98% | 24666 | 139896 | 14.99%
Total Participation |  |  | 25666 | 145509 | 14.99% | 26385 | 149647 | 14.99%
Annual Energy Savings (dth)
Residential - Efficient Products | HVAC | Core | 2247.0376 | 17036.4956 | 11.65% | 4415.3502 | 31590.5895 | 12.26%
| Appliance Rebates | Core | 29.9591 | 192.3894 | 13.47% | 53.9755 | 365.7696 | 12.86%
| Online Marketplace | Core | 3307.509 | 16064.429 | 17.07% | 4862.028 | 23604.624 | 17.08%
| EE Giveaway Kits | Core | 0 | 3.2282 | 0% | 0 | 3.2282 | 0%
Residential - Existing Homes | Home Performance with Energy Star | Core | 55.3356 | 502.7647 | 9.915% | 55.3356 | 832.812 | 6.23%
| Quick Home Energy Check-Up | Additional | 137.4694 | 923.9557 | 12.95% | 461.1162 | 1208.937 | 27.61%
| Moderate Income Weatherization | Additional | 312.3103 | 1249.9608 | 19.99% | 659.5927 | 3450.7234 | 16.05%
Behavioral | Behavioral | Additional | 6203.696 | 35234.504 | 14.97% | 7879.665 | 44753.335 | 14.97%
C&I Direct Install | Direct Install | Core | 267.308 | 1108.7677 | 19.43% | 1829.5657 | 2372.8868 | 43.54%
Energy Solutions for Business | Prescriptive/Custom | Core | 467.7731 | 185.4169 | 71.61% | 467.7731 | 216.8887 | 68.32%
| Energy Management | Additional | 0 | 0 | N/A | 0 | 0 | N/A
| Engineered Solutions | Additional | 0 | 0 | N/A | 0 | 0 | N/A
Multi-Family | Multi-Family Home Performance with Energy Star | Core | 0 | 328.4 | 0% | 0 | 328.4 | 0%
| Multi-Family Direct Install | Core | 0 | 356.9443 | 0% | 32.2915 | 1300.7338 | 2.422%
| Multi-Family Prescriptive / Custom | Core | 0 | 0 | N/A | 129.3511 | 0 | 100%
| Multi-Family Engineered Solutions | Core | 0 | 2348.499 | 0% | 0 | 2348.499 | 0%
Total Core Annual Energy Savings |  |  | 6374.9223 | 38127.3347 | 14.32% | 11845.6705 | 62964.4317 | 15.83%
Total Additional Annual Energy Savings |  |  | 6653.4757 | 37408.4205 | 15.1% | 9000.3739 | 49412.9953 | 15.41%
Total Annual Energy Savings |  |  | 13028.398 | 75535.7552 | 14.71% | 20846.0444 | 112377.427 | 15.65%
Lifetime Energy Savings (dth)
Residential - Efficient Products | HVAC | Core | 42770.0679 | 322252.8666 | 11.72% | 83449.6304 | 595643.7023 | 12.29%
| Appliance Rebates | Core | 352.7497 | 2260.1236 | 13.5% | 634.9099 | 4297.2257 | 12.87%
| Online Marketplace | Core | 24849.7205 | 120718.468 | 17.07% | 36590.077 | 177509.961 | 17.09%
| EE Giveaway Kits | Core | 0 | 30.966 | 0% | 0 | 30.966 | 0%
Residential - Existing Homes | Home Performance with Energy Star | Core | 1398.6918 | 12081.1394 | 10.38% | 1398.6918 | 20901.4787 | 6.272%
| Quick Home Energy Checkup | Additional | 1383.7998 | 9312.6618 | 12.94% | 4628.2434 | 12186.3452 | 27.53%
| Moderate Income Weatherization | Additional | 5536.1291 | 25736.0911 | 17.7% | 13268.4807 | 66953.8396 | 16.54%
Behavioral | Behavioral | Additional | 6203.696 | 35234.504 | 14.97% | 7879.665 | 44753.335 | 14.97%
C&I Direct Install | Direct Install | Core | 4028.188 | 16579.1664 | 19.55% | 28370.3854 | 37777.9591 | 42.89%
Energy Solutions for Business | Prescriptive/Custom | Core | 9188.2318 | 3514.6954 | 72.33% | 9188.2318 | 4144.1314 | 68.92%
| Energy Management | Additional | 0 | 0 | N/A | 0 | 0 | N/A
| Engineered Solutions | Additional | 0 | 0 | N/A | 0 | 0 | N/A
Multi-Family | Multi-Family Home Performance with Energy Star | Core | 0 | 8620.5 | 0% | 0 | 8620.5 | 0%
| Multi-Family Direct Install | Core | 0 | 3569.4428 | 0% | 322.9147 | 13007.338 | 2.422%
| Multi-Family Prescriptive / Custom | Core | 0 | 0 | N/A | 1940.2659 | 0 | 100%
| Multi-Family Engineered Solutions | Core | 0 | 37858.724 | 0% | 0 | 37858.724 | 0%
Total Core Lifetime Energy Savings |  |  | 82587.6496 | 527486.0922 | 13.54% | 161895.107 | 899791.9862 | 15.25%
Total Additional Participation |  |  | 13123.6249 | 70283.2568 | 15.73% | 25776.3892 | 123893.5198 | 17.22%
Total Lifetime Energy Savings |  |  | 95711.2746 | 597769.349 | 13.8% | 187671.4961 | 1023685.506 | 15.49%
1 Across all programs, participation/expenditures/savings are classified as either in an Environmental Justice Overburdened Community census block or not based on the program participant’s address. Overburdened Community census blocks were developed and defined by the NJ Department of Environmental Protection (www.nj.gov/dep/ej/communities.html). The Overburdened Community (OBC) census blocks are defined with three criteria: at least 35% of households qualify as low-income, at least 40% of residents identify as minority, and at least 40% of households have limited English proficiency. If any of the three criteria is satisfied, the census block is defined as OBC. Staff directed to only include OBC census blocks where at least 35% of households qualify as low-income. For example, a census block that only satisfies the limited English proficiency criteria is not included.
2 The %OBC column shows the ratio of the overburdened metric over the total of overburdened plus non-overburdened. Comparing the territory-level benchmark %OBC (upper table) versus the program %OBC (lower table) shows how equitable the distribution of the program is between the overburdened and non-overburdened populations. If the program %OBC is greater than the benchmark %OBC, then the overburdened population is better represented in the program relative to the percentage of overburdened households or business in the utility territory.
3 Estimation of accounts with overburdened designation determined to be active immediately preceding the current Plan Year.
4 Estimation of usage with overburdened designation for the 12-month period immediately preceding the current Plan Year.

## Table 8 (hidden)
Table 8 - Benefit-Cost Test Results By Program
| Initial | [5 empty] | Final
| NJCT | PCT | PACT | RIMT | TRCT | SCT | NJCT | PCT | PACT | RIMT | TRCT | SCT
Res Efficient Products | 1.6913 | 7.6873 | 0.88904 | 0.55796 | 0.69537 | 2.31
Res Existing Homes | 1.5948 | 4.8945 | 1.2081 | 0.72343 | 0.77419 | 2.4269
Res Income Eligible | 1.1567 | n/a | 0.53532 | 0.40193 | 0.53532 | 1.8431
Res Behavioral Energy | 2.1674 | n/a | 1.1974 | 0.61764 | 1.1974 | 2.5803
Multifamily | 1.3206 | n/a | 0.68737 | 0.46104 | 0.68737 | 2.4212
C&I Small Non-Residential Efficiency | 2.6592 | 5.3822 | 1.8723 | 1.101 | 1.2802 | 4.2927
C&I Prescriptive | 2.7131 | 6.5543 | 2.044 | 1.1646 | 1.2795 | 3.5345
C&I Custom | 3.0087 | 6.925 | 2.1024 | 1.2615 | 1.4896 | 4.7426
C&I Energy Management | 1.7697 | 8.6919 | 1.4347 | 0.99433 | 1.2555 | 4.0476
C&I Engineered Solutions | 1.7778 | 5.2821 | 1.1178 | 0.87086 | 0.88671 | 3.0374

## Ap A - Participant Def (hidden)
In Word document only

## Ap A - Participant Def.
In Word document only

## Ap B - Participant-Spend
SJG Energy Efficiency and PDR Savings Summary
South Jersey Gas Quarterly Report - Appendix B
For Period Ending PY24Q2
|  |  | Participation |  |  |  | Actual Expenditures
|  |  | A | B | C | D=C/B | E | F | G | H=G/F
|  |  | Quarter | Annual Forecasted Participation Number | YTD Reported Participation Number | YTD % of Annual Participants | Quarter ($000) | Annual Forecasted Program Costs ($000)² | YTD Reported Program Costs ($000) | YTD % of Annual Budget
| Residential Programs | Sub Program or Category¹
| Efficient Products* | HVAC | 1396 |  | 3009 |  | 4526.8209 |  | 9128.806
|  | Appliance Rebates | 516 |  | 976 |  | 133.055 |  | 253.6317
|  | Marketplace Efficient Products | 4837 |  | 7142 |  | 562.4566 |  | 825.7302
|  | EE Giveaway Kits | 1 |  | 1 |  | 0.0269 |  | 0.0269
|  | Subtotal Efficient Products | 6750 | 40456 | 11128 | 27.51% | 5222.3594 | 23828.1317 | 10208.1948 | 42.84%
| Existing Homes | Home Performance with Energy Star* | 35 | 360 | 57 | 15.83% | 667.1988 | 5275.9497 | 1138.5574 | 21.58%
|  | Quick Home Energy Check-Up | 191 | 1500 | 295 | 19.67% | 102.8442 | 1067.4446 | 166.5593 | 15.6%
|  | Moderate Income Weatherization | 87 | 700 | 247 | 35.29% | 725.6866 | 7715.7195 | 1672.2807 | 21.67%
| Behavioral | Behavioral | 164020 | 150000 | 164020 | 109.3% | 240.5857 | 1043.6873 | 496.0288 | 47.53%
| Total Residential |  | 171083 | 193016 | 175747 | 91.05% | 6958.6747 | 38930.9327 | 13681.6209 | 35.14%
| Business Programs | Sub-Program
| C&I Direct Install | Direct Install* | 2 | 25 | 9 | 36% | 395.7987 | 2086.7297 | 1334.1515 | 63.94%
| Energy Solutions for Business | Prescriptive/Custom*³ | 7 | 1133 | 8 | 0.7061% | 92.79 | 1244.3048 | 166.5018 | 13.38%
|  | Energy Management | 0 | 5 | 0 | N/A | 14.5886 | 600.1952 | 27.6945 | N/A
|  | Engineered Solutions | 0 | 1 | 0 | N/A | 29.8784 | 2402.7642 | 55.1258 | N/A
| Total Business |  | 9 | 1164 | 17 | 1.46% | 533.0556 | 6333.994 | 1583.4736 | 25%
| Multi-Family* | HPwES | 48 |  | 48 |  | 65.118 |  | 71.4077
|  | Direct Install | 80 |  | 264 |  | 41.6242 |  | 98.5281
|  | Prescriptive/Custom* | 0 |  | 1 |  | 4.0689 |  | 4.8743
|  | Engineered Solutions | 1 |  | 1 |  | 618.5371 |  | 682.226
|  | Subtotal Multi-Family | 129 | 1353 | 314 | 23.21% | 729.3482 | 3129.6223 | 857.0361 | 27.38%
Other Programs
Home Optimization & Peak Demand Reduction
Total Other
| Portfolio Total |  | 171221 | 195533 | 176078 | 90.05% | 8221.0785 | 48394.5489 | 16122.1307 | 33.31%
1 Subprograms provide relevant forecasts as included in the Company's approved EE/PDR Plans. Program delivery elements are generally listed as categories for informational purposes only.
2 Annual Forecasted Program Costs reflect values anticipated in Board-approved Utility EE/PDR filings and may incorporate budget adjustments as provided for in the June 10, 2020 Board Order.
3 Prescriptive/Custom Participation Number is reported on a Measure level.
* Denotes a core EE program. Home Performance with Energy Star only includes non-LMI; the comparable program for LMI participants is Comfort Partners, which is jointly administered by the State and Utilities.

## Ap B - Qtr NG Master
SJG Energy Efficiency and PDR Savings Summary
South Jersey Gas Quarterly Report - Appendix B
For Period Ending PY24Q2
Ex Ante Energy Savings
|  |  | I | J | K | L=K/J | M | N | O | P
|  |  | Quarter Annual Retail Energy Savings (DTh) | Annual Forecasted Retail Energy Savings (DTh) | YTD Reported Retail Energy Savings (DTh) | YTD % of Annual Energy Savings | YTD Reported Wholesale Energy Savings (DTh) | YTD Peak Demand Savings (DT)3 | Quarter Lifetime Retail Savings (DTh)4 | YTD Lifetime Retail Savings (DTh)4
| Residential Programs | Sub Program or Category¹
| Efficient Products* | HVAC | 19283.5332 |  | 36005.9397 |  | 36528.2943 |  | 365022.9345 | 679093.3327
|  | Appliance Rebates | 222.3485 |  | 419.7451 |  | 425.8345 |  | 2612.8733 | 4932.1357
|  | Marketplace Efficient Products | 19371.938 |  | 28466.652 |  | 28879.6307 |  | 145568.1885 | 214100.038
|  | EE Giveaway Kits | 3.2282 |  | 3.2282 |  | 3.275 |  | 30.966 | 30.966
|  | Subtotal Efficient Products | 38881.0478 | 161982.2 | 64895.565 | 40.06% | 65837.0346 | 0 | 513234.9623 | 898156.4724
| Existing Homes | Home Performance with Energy Star* | 558.1002 | 11876.6 | 888.1475 | 7.478% | 901.0323 |  | 13479.8312 | 22300.1705
|  | Quick Home Energy Check-Up | 1061.4251 | 4240.4 | 1670.0532 | 39.38% | 1694.2814 |  | 10696.4616 | 16814.5887
|  | Moderate Income Weatherization | 1562.2711 | 11507.2 | 4110.316 | 35.72% | 4169.9463 |  | 31272.2202 | 80222.3203
| Behavioral | Behavioral | 41438.2 | 46664.2 | 52633 | 112.8% | 53396.571 |  | 41438.2 | 52633
| Total Residential |  | 83501.0442 | 236270.6 | 124197.0817 | 52.57% | 125998.8655 | 0 | 610121.6752 | 1070126.5518
| Business Programs | Sub-Program
| C&I Direct Install | Direct Install* | 1376.0757 | 3452.2 | 4202.4525 | 121.7% | 4263.4194 |  | 20607.3544 | 66148.3446
| Energy Solutions for Business | Prescriptive/Custom*2 | 653.19 | 10630.5 | 684.66 | 6.441% | 694.5927 |  | 12702.9271 | 13332.3631
|  | Energy Management | 0 | 1209.2 | 0 | N/A | 0 |  | 0 | 0
|  | Engineered Solutions | 0 | 4391.8 | 0 | N/A | 0 |  | 0 | 0
| Total Business |  | 2029.2657 | 19683.7 | 4887.1125 | 24.83% | 4958.0121 | 0 | 33310.2816 | 79480.7077
| Multi-Family* | HPwES | 328.4 |  | 328.4 |  | 333.1642 |  | 5582.8 | 5582.8
|  | Direct Install | 356.9443 |  | 1333.0253 |  | 1352.3641 |  | 3569.4428 | 13330.2527
|  | Prescriptive/Custom* | 0 |  | 129.35 |  | 131.2265 |  | 0 | 1940.2659
|  | Engineered Solutions | 2348.5 |  | 2348.5 |  | 2382.5708 |  | 37858.724 | 37858.724
|  | Subtotal Multi-Family | 3033.8443 | 4276.8 | 4139.2753 | 96.78% | 4199.3256 | 0 | 47010.9668 | 58712.0426
Other Programs
Home Optimization & Peak Demand Reduction
Total Other
| Portfolio Total |  | 88564.1542 | 260231.1 | 133223.4695 | 51.19% | 135156.2032 | 0 | 690442.9236 | 1208319.3021
1 Subprograms provide relevant forecasts as included in the Company's approved EE/PDR Plans. Program delivery elements are generally listed as categories for informational purposes only.
2 Prescriptive/Custom Participation Number is reported on a Measure level
3 On-going discussions within the Evaluation, Measurement and Verification (EM&V) Working Group have noted that there is no clearly defined protocol for calculating Peak Demand Savings for natural gas measures. It is anticipated that this issue will be
addressed by the EM&V Working Group within this Triennial. No Peak Demand Savings for natural gas measures will be reported until an agreed upon methodology has been determined.
4 Quarter Lifetime Retail Savings and YTD Lifetime Retail Savings for Behavioral is calculated based on a 1 year Measure Life
* Denotes a core EE program. Home Performance with Energy Star only includes non-LMI; the comparable program for LMI participants is Comfort Partners, which is jointly administered by the State and Utilities.

## Ap C - Qtr NG LMI
Energy Efficiency and PDR Savings Summary
South Jersey Gas Quarterly Report - Appendix C
For Period Ending PY24Q2
|  |  | Participation |  | Incentive Expenditures (Customer Rebates and Low/no-cost financing) |  | Ex Ante Energy Savings |  | Participation
|  |  | A | B | C | D | E | F
|  |  | Reported Participation Number YTD |  | Reported Incentive Costs YTD ($000) |  | Reported Retail Energy Savings YTD (DTh)
| Residential Programs | Sub Program | LMI | Non-LMI or Unverified | LMI | Non-LMI or Unverified | LMI | Non-LMI or Unverified
| Efficient Products | HVAC | 73 | 2936 | 319.9523 | 8428.5304 | 849.9445 | 35155.9952
|  | Appliance Rebates | 0 | 1 | 0 | 0.0269 | 0 | 3.2282
|  | Marketplace Efficient Products | 0 | 7142 | 0 | 699.9685 | 0 | 28466.652
|  | Efficient Products Kits | 0 | 976 | 0 | 138.95 | 0 | 419.7451
|  | Subtotal Efficient Products | 73 | 11055 | 319.9523 | 9267.4758 | 849.9445 | 64045.6205
| Existing Homes | Home Performance with Energy Star1 | 0 | 57 | 0 | 861.3755 | 0 | 888.1475
|  | Quick Home Energy Check-Up | 0 | 295 | 0 | 89.2883 | 0 | 1670.0532
|  | Moderate Income Weatherization | 247 | 0 | 1340.39 | 0 | 4110.316 | 0
| Behavioral | Behavioral | 0 | 164020 | 0 | 441.4477 | 0 | 52633
| Total Residential |  | 320 | 175427 | 1404.94 | 3132.12 | 4960.2606 | 119236.8212
| Multi-Family | HPwES | 0 | 48 | 0 | 52.8 | 0 | 328.4
|  | Direct Installation/MF QHEC | 0 | 264 | 0 | 31.5345 | 0 | 1333.0253
Total Multifamily
Home Optimization & Peak Demand Reduction
| Total Other |  | 0 | 0 | 0 | 0 | 0 | 0
| Portfolio Total |  | 320 | 175739 | 1404.94 | 3216.4545 | 4960.2606 | 120898.2464
Supportive Costs Outside Portfolio
1 Income-qualified customers are directed to participate through the Comfort Partners or Moderate Income Weatherization programs.

## Ap D - Qtr NG Business Class
Energy Efficiency and PDR Savings Summary
South Jersey Gas Quarterly Report - Appendix D
For Period Ending PY24Q2
|  |  | Participation |  | Incentive Expenditures (Customer Rebates and Low/no-cost financing) |  | Ex Ante Energy Savings |  | Participation
|  |  | A | B | C | D | E | F
|  |  | Reported Participation Number YTD |  | Reported Incentive Costs YTD ($000) |  | Reported Retail Energy Savings YTD (DTh)
| Business Programs | Sub-Program | Small Commercial | Large Commercial | Small Commercial | Large Commercial | Small Commercial | Large Commercial
| C&I Direct Install | Direct Install | 9 | 0 | 1194.94 | 0 | 4202.4525 | 0
| Energy Solutions for Business | Prescriptive/Custom | 2 | 6 | 1 | 46.53 | 15.89 | 668.77
|  | Energy Management | 0 | 0 | 0 | 0 | 0 | 0
|  | Engineered Solutions | 0 | 0 | 0 | 0 | 0 | 0
| Total Business |  | 11 | 6 | 1195.94 | 46.53 | 4170.28 | 668.77
| Multi-Family | Prescriptive/Custom | 0 | 1 | 0 | 0.75 | 0 | 129.35
|  | Engineered Solutions | 0 | 1 | 0 | 544.9766 | 0 | 2348.5
| Other Programs |  | 0 | 2 | 0 | 545.7266 | 0 | 2477.85
Home Optimization & Peak Demand Reduction
| Total Other |  | 0 | 0 | 0 | 0 | 0 | 0
| Portfolio Total |  | 11 | 8 | 1195.94 | 592.2566 | 4170.28 | 3146.62
Supportive Costs Outside Portfolio

## Ap E - NJ CEA Benchmarks
Appendix E Quarterly Report Baseline Calculation
For Period Ending PY24Q2
Energy Efficiency Compliance Baselines and Benchmarks (therms)
Gas Utility | Plan Year | Sales Period | Sales (therms) | Adjustments | Adjusted Retail Sales | Compliance Baseline | Overall Annual Energy Reduction Target (%) | Overall Annual Energy Reduction Target (therms) | State-Administered Annual Energy Reduction Target (%) | State-Administered Annual Energy Reduction Target (therms) | Utility-Administered Annual Energy Reduction Target (%) | Utility-Administered Annual Energy Reduction Target (therms)
|  |  | (A) | (B) | (C) = (A)-(B) | (D)=Average (C) | (E) | (F) = (E) * (D) | (G) | (H) = (G) * (D) | (I) | (J) = (I) * (D)
South Jersey Gas | 2019 | 7/1/18 - 6/30/19 | 574069243.4 | 45731812.7 | 528337430.7
| 2020 | 7/1/19 - 6/30/20 | 529105554.2 | 42406213.6 | 486699340.6
| 2021 | 7/1/20 - 6/30/21 | 551325543.4 | 36813249.6 | 514512293.8
| 2022 | 7/1/21 - 6/30/22 | 544182719 | 32515573.6 | 511667145.4
| 2023 | 7/1/22 - 6/30/23 | 533374477.5 | 32370546.5 | 501003931 | 509061123.4 | 0.75% | 3817958.4255 | 0.24% | 1221746.6962 | 0.51% | 2596211.7293
Notes:
(A) Includes sales as reported on FERC Form-2, as adjusted for the given sales period (planning year)
(B) Includes adjustments to remove Electric Generation.

## SJG
Reporting Period | FY23-Q3
Program/Utility Information |  |  |  | Participants | Budget & Expenses ($000) |  |  | Energy Savings
Utility | Sector | Program | Sub-Program | YTD Reported Participation Number | Annual Budget | Reported Incentive Costs YTD | YTD Reported Program Costs | YTD Annual Electric Savings (MWh) | YTD Lifetime Electric Savings (MWh) | YTD Peak Demand Electric Savings (MW) | YTD Annual Gas Savings (Dtherm) | YTD Lifetime Gas Savings (Dtherm)
SJG | Residential | Efficient Products | HVAC | 3009 |  | 8748.4827 | 9128.806 |  |  |  | 36005.9397 | 679093.3327
SJG | Residential | Efficient Products | Appliance Rebates | 976 |  | 0.0269 | 253.6317 |  |  |  | 419.7451 | 4932.1357
SJG | Residential | Efficient Products | Marketplace Efficient Products | 7142 |  | 699.9685 | 825.7302 |  |  |  | 28466.652 | 214100.038
SJG | Residential | Efficient Products | EE Giveaway Kits | 1 |  | 138.95 | 0.0269 |  |  |  | 3.2282 | 30.966
SJG | Residential | Efficient Products |  |  | 23828.1317
SJG | Residential | Existing Homes | Home Performance with Energy Star* | 57 | 5275.9497 | 861.3755 | 1138.5574 |  |  |  | 888.1475 | 22300.1705
SJG | Residential | Existing Homes | Quick Home Energy Check-Up | 295 | 1067.4446 | 89.2883 | 166.5593 |  |  |  | 1670.0532 | 16814.5887
SJG | Residential | Existing Homes | Moderate Income Weatherization | 247 | 7715.7195 | 1340.39 | 1672.2807 |  |  |  | 4110.316 | 80222.3203
SJG | Residential | Behavioral | Behavioral | 164020 | 1043.6873 | 441.4477 | 496.0288 |  |  |  | 52633 | 52633
SJG | Comfort Partners | Comfort Partners | Comfort Partners | 291 | 4289.861 |  | 2228.0583 |  |  |  | 1337.5896 | 20938.6269
SJG | Commercial | Direct Install | Direct Install | 9 | 2086.7297 | 1194.94 | 1334.1515 |  |  |  | 4202.4525 | 66148.3446
SJG | Commercial | Energy Solutions for Business | Prescriptive/Custom*³ | 8 | 1244.3048 | 47.53 | 166.5018 |  |  |  | 684.66 | 13332.3631
SJG | Commercial | Energy Solutions for Business | Energy Management | 0 | 600.1952 | 0 | 27.6945 |  |  |  | 0 | 0
SJG | Commercial | Energy Solutions for Business | Engineered Solutions | 0 | 2402.7642 | 0 | 55.1258 |  |  |  | 0 | 0
SJG | Multi-Family | Multi-Family | HPwES | 48 |  | 52.8 | 71.4077 |  |  |  | 328.4 | 5582.8
SJG | Multi-Family | Multi-Family | Direct Install | 264 |  | 31.5345 | 98.5281 |  |  |  | 1333.0253 | 13330.2527
SJG | Multi-Family | Multi-Family | Prescriptive/Custom* | 1 |  | 0.75 | 4.8743 |  |  |  | 129.35 | 1940.2659
SJG | Multi-Family | Multi-Family | Engineered Solutions | 1 |  | 544.9766 | 682.226 |  |  |  | 2348.5 | 37858.724
SJG | Multi-Family | Multi-Family |  |  | 3129.6223
SJG | Pilot Program | Home Optimization & Peak Demand Reduction | Home Optimization & Peak Demand Reduction | 0 | 0 | 0 | 0 |  |  |  | 0 | 0

## AP F - Secondary Metrics (hidden)
Appendix F – Energy Savings with FY2022 TRM Addendum
For compliance purposes throughout the first triennium, the utilities calculate program savings (collectively, "Primary Metrics") based on a mix of protocols from the FY20 NJCEP Protocols, FY21 NJCEP Protocols Addendum, and TRMs from other states when no applicable NJ-specific measure calculation is available. This mix of protocols is cataloged in the Joint Utility Coordinated Measures List. The EM&V Working Group created the 2022 TRM Addendum to address key non-NJ specific and dated assumptions in the Coordinated Measures List. Program Energy Savings Metrics calculated with the 2022 TRM Addendum are called the “Secondary Metrics”. The Secondary Metric values are informational for stakeholders to assess program performance under a more current and NJ-specific measure calculation approach and to inform future program design.
Table F-1 – Sector-Level Energy Savings: Primary Metrics from 2020/21 TRM
Annual Energy Savings1 | Annual Retail (MWh) | Annual Target Retail Savings (MWh) | Percent of Annual Target | Annual Retail (Dth) | Annual Target Retail Savings (Dth) | Percent of Annual Target |  | Primary Metric Electric (MWh) - 2020/21 TRM | Secondary Metric Electric (MWh) 2022 TRM | Primary Metric - Gas (Dth) - 2020/21 TRM | Secondary Metric - Gas (Dth) - 2022 TRM
Residential | #REF! | #REF! | #REF! | 124197.0817 | 236270.6 | 52.57% | Annual Savings | #REF! | 0 | 133223.4695 | 0
Multifamily | #REF! | #REF! | #REF! | 4139.2753 | 4276.8 | 96.78% | Lifetime Savings | #REF! | 3625802.1097
C&I | #REF! | #REF! | #REF! | 4887.1125 | 19683.7 | 24.83%
Reported Totals for Utility Administered Programs | #REF! | #REF! | #REF! | 133223.4695 | 260231.1 | 51.19% | Figure F-1 - Program Year [2022] Portfolio-Level Annual Energy Savings – Primary vs. Secondary Metrics
Table F-2 – Sector-Level Energy Savings: Secondary Metrics from 2022 TRM Addendum
Annual Energy Savings1 | Annual Retail (MWh) | Annual Target Retail Savings (MWh) | Percent of Annual Target | Annual Retail (Dth) | Annual Target Retail Savings (Dth) | Percent of Annual Target
Residential |  |  |  |  | 236270.6 | 0%
Multifamily |  |  |  |  | 4276.8 | 0%
C&I |  |  |  |  | 19683.7 | 0%
Reported Totals for Utility Administered Programs | 0 | 0 | #DIV/0! | 0 | 260231.1 | 0%
1 Annual energy savings represent the total expected annual savings from all energy efficiency measures within each sector, and not only those measures affected by the FY2022 TRM Addendum.
Figure F-2 - Program Year [2022] Portfolio-Level Lifetime Energy Savings – Primary vs Secondary Metrics

## AP G - Transfer (hidden)
Appendix G - Ex-ante Energy Savings held by Utility for Transfer
The following data are presented to provide Board Staff visibility into the full picture of statewide annual ex-ante energy projects in progress, with these energy savings being excluded from data presented in the body of the report. These data are based upon coordinated program projects completed by a lead utility and awaiting transfer to a partner utility. The data presented are estimates and are subject to change during transfer to and verification by partner utilities. Transferred savings and associated costs will be included in partner utility results once allocated by the Statewide Coordination platform.
Estimated Annual Energy Savings Held by (insert Utility name)
Program | Dth held for transfer | MWh held for transfer
Res Efficient Products
RES Existing Homes
Income Eligible Weatherization
RES Multifamily
C&I DI Small Non-Res
C&I Prescriptive
C&I Custom
C&I Energy Management
C&I Engineered Solutions
Total | 0 | 0

## AP H - CostTest (hidden)
Appendix H - Cost Effectiveness Test Details |  | Thousands ($)
|  | Residential | Business | MF | Total Portfolio
Total Resource Cost Test (TRC)
1 | Lifetime Avoided Electric Supply Costs
2 | Lifetime Avoided Electric Capacity Costs
3 | Lifetime Avoided Natural Gas Supply Costs
4 | Lifetime Merit Order (DRIPE) Benefits
5 | Lifetime REC Avoided Purchases
6 | Lifetime Wholesale Volatility Value
7 | Lifetime Avoided T&D Costs
Total Benefit = 1+2+3+4+5+6+7
8 | Lifetime Participant Costs
9 | Lifetime Administration Costs
10 | Lifetime Program Investment Costs
Total Costs (9+10+11)
Benefit Cost Ratio = (1+2+3+4+5+6+7)/(8+9+10)
Particpant Cost Test (PCT)
11 | Lifetime Participant Benefits
12 | Lifetime Repayment Benefits
Benefit Cost Ratio = (10+11+12)/(8+10)
Program Administrator Cost Test (PAC)
Benefit Cost ratio = (1+2+3+4+5+6+7)/(9+10+12)
Ratepayer Impact Measure Test (RIM)
13 | Lifetime utility Revenue Gained
14 | Lifetime Utility Cost
Benefit Cost ratio = (1+2+3+4+5+6+7+13)/(9+10+12+14)
Societal Cost Test (SCT)
15 | Lifetime Avoided Electric Supply Costs
16 | Lifetime Avoided Electric Capacity Costs
17 | Lifetime Avoided Natural Gas Supply Costs
18 | Lifetime Merit Order (DRIPE) Benefits
19 | Lifetime REC Avoided Purchases
20 | Avoided Wholesale Volatility Costs
21 | Lifetime Avoided T&D Costs
22 | Lifetime Avoided Emission Benefit
23 | Lifetime Economic Multiplier Benefit
Total Benefit = (15+16+17+18+19+20+21+22+23)
24 | Lifetime Participant Costs
25 | Lifetime Administration Costs
26 | Lifetime Program Investment Costs
Total Costs = (24+25+26)
Benefit Cost Ratio = (16+17+18+19+20+21+22+23+24)/(24+25+26)
New Jersey Cost Test (NJCT)
27 | Lifetime Avoided Electric Supply Costs
28 | Lifetime Avoided Electric Capacity Costs
29 | Lifetime Avoided Natural Gas Supply Costs
30 | Lifetime Merit Order (DRIPE) Benefits
31 | Lifetime Merit Order (DRIPE) Capacity Benefits
32 | Lifetime Avoided T&D Costs
33 | Lifetime Avoided Ancillary Services Costs
34 | Lifetime Avoided Emission Benefit
35 | Lifetime Non Energy Benefits x 5%
Total Benefit = 27+28+29+30+31+32+33+34+35
Benefit Cost Ratio = (27+28+29+30+31+32+33+34+35)/(24+25+26)
Net Present Value of Utility Cost Test Net Benefits (Thousands $)
NPV = (1+2+3+4+5+6+7) - (9+10+12) |  |  |  |  | 0

## AP I - Program Changes (hidden)
In Word document only