## Site Statistics
Site | Property Owner | Cost per Project ($k) | NPV of 20 Year Lease Cost ($k) | EPC Contractor | Site Location Address | Owner location | Type of customer | Status of the installation | Capacity of Project (MW-DC) | Equipment installed (Inverters; Panels)
Segment 1a
Linden | PSE&G |  | N/A | ASP | South Wood Avenue, Linden, NJ 07036 | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 3.1969 | Three Sunny Central 1000-US inverters; 7,766 Suntech STP280-24/Vd, 3,718 STP275-24/Vd panels
Yardville | PSE&G |  | N/A | ACE | Broad Street, Hamilton, NJ 08611 | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 4.3024 | Fifty five Chint power system inverters; 5,640 Suntech STP270-24/VD, 4,368 STP275-24/VD, 1,512 STP280-24/VD panels
Silver Lake | PSE&G |  | N/A | JFC | 410 Silver Lake Avenue, Edison, NJ 08817 | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 2.0176 | Forty seven Chint power system inverters; 3,514 Sharp ND-224UC1, 5,236 ND-U235F1
Trenton | PSE&G |  | N/A | SunEdison | 500-520 Brunswick Avenue, Trenton, NJ 08638 | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 1.2641 | Thirty nine SMA Core 1 inverters; 5,496 Yingli Solar YL230b-29b panels
Central HQ | PSE&G |  | N/A | Solis (Solyndra) | 472 Weston Canal Road, Franklin, NJ 08873 | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 0.91628 | 10 SMA Tripower 15kw inverters, 29 SMA Tripower 20kw Inverters; 4,180 Solyndra SL-001-182U, 648 Solar World SW240MONO panels
Edison Training | PSE&G |  | N/A | Henkle & McCoy | 234 Pierson Avenue, Edison, NJ 08837 | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 0.7119 | 7 50kw SMA Tripower inverters, 1 30kw SMA Inverter, 4 24kw SMA Inverter, 10 15kw SMA Inverter; 3,164 Gloria Solar GSM6-225D-E1 panels
Thorofare | PSE&G |  | N/A | SunEdison | Jessup Road, Thorofare, NJ 08086 | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 0.71995 | Sixteen Chint power system inverters; 2,618 SunTech STP275-24Vd panels
Hackensack | PSE&G |  | N/A | JFC | 194-210 South River Street, Hackensack NJ 07601 | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 1.0509 | Thirty SMA Core 1 inverters, 4,472 MX Solar MX-60-235 panels
Metro/Clifton | PSE&G |  | N/A | Gloria Solar | 150 Circle Ave, Clifton, NJ 07011 | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 0.73335 | Four Satcon Powergate Plus PVS-75, two PVS-135 inverters; 3,122 Gloria Solar GSM6-235D-E1 panels
S. DivHQ Moorestown | PSE&G |  | N/A | Vanguard | 360 New Albany Road, Moorestown, NJ | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 1.0723 | Twenty nine Chint system inverters . 4,563 MX60-235 panels
Segment 1b
CPP Bayonne | CenterPoint Properties |  | 1402 | ASP | 30-100 Pulaski Street, Bayonne, NJ 07002 | 1808 Swift Drive, Oak Brook, IL 60523-1501 | Warehouse | Commercial Operation | 1.7032 | 15 SolarEdge SE100KUS inverters and three SolarEdge SE33.3KUS inverters; 7,730 Trina Solar TSM-220PA05 panels
Matrix - Stults Rd | Matrix Development Group |  | 2228 | Pro-Tech | 45 Stults Rd, 'South Brunswick, NJ 08810 | Forsgate Drive CN 4000, Cranbury, NJ 08512 | Warehouse | Commercial Operation | 2.9807 | Five Solaron 3159500-1001AD inverters; 12,684 Kyocera K0235GX-LPB panels
Rider | Rider University |  | 642 | Alteris | 2083 Lawrenceville Road, Lawrenceville, NJ 08648 | 2083 Lawrenceville Road, Lawrenceville, NJ 08548 | University | Commercial Operation | 0.7392 | Sixteen Chint system inverters; 2,640 Suntech STP-280 panels
NJMC / Kearny Landfill | NJ Meadowland Commission |  | 2561 | Sundurance | 932 Bellville Turnpike, Kearny, Hudson County NJ 07032 | One DeKorte Park Plaza, Lyndhurst, NJ 07071 | Landfill | Commercial Operation | 3.001 | Seven Advanced Energy Solaron inverters 2x500kW, 3x333kW, 2x250kW; 12,506 Kyocera KD240GX-LFB panels
Mill Creek | Judith Tucci |  | 3189 | Juwi | 600 Irick Road, Westampton, NJ 08060 | 4 St. Albans Place, Haworth, NJ 07641 | Private Landowner | Commercial Operation | 3.822 | Fifteen SMA Core 1 33 inverters and 3 SMA Sunny Central 1000-US inverters; 29,400 Solar Frontier SF-130-L panels
Food Bank | Community Food Bank of NJ |  | 772 | Mercury | 31 Evans Terminal, Hillside, NJ 07250 | 31 Evans Terminal Rd, Hillside, New Jersey 07250 | Warehouse | Commercial Operation | 1.0734 | 121 ProHarvest HiQ Inverters; 4,667 Trina Solar TSM-230PA05 panels
Raritan Center | Summit Associates Inc. |  | 1729 | ASP | 45 Fernwood Avenue and 110 Fieldcrest Avenue, Edison, NJ 08818 | Raritan Plaza I, Edison, NJ 08818 | Warehouse | Commercial Operation | 2.2236 | 235 ProHarvest HiQ inverters; 7,098 Hyundai HIS-M230SG, 2,604 HIS-M227SG panels
BlackRock-Matrix | Granite South Brunswick, LLC |  | 1800 | Pro-Tech | 140 Docks Corner Road, South Brunswick, NJ 08810 | BlackRock, 40 E. 52nd Street, New York, NY 10022 | Warehouse | Commercial Operation | 2.9702 | Five AE Solaron 3159000-1001AJ inverters; 12,376 Upsolar UP-M240P panels
Segment 1c
Matrix Bldg A & B | Matrix Development |  | 2191 | enXco | 1000 & 1050 Amboy Ave, Perth Amboy, NJ 08861 | Forsgate Drive CN 4000, Cranbury, NJ 08512 | Warehouse | Commercial Operation | 2.8586 | 300 ProHarvest HiQ inverters; 10,395 Suntech STP275-24VD panels
Barringer | Newark Public Schools |  | 635 | Mercury | 90 Parker St, Newark, NJ 07104 | Newark Public Schools, 2 Cedar Street, Newark NJ 07102-3051 | Public Schools | Commercial Operation | 0.6468 | 73 ProHarvest HiQ inverters; 2,310 Suntech STP280-24VB-1 panels
Park | Newark Public Schools |  | 482 | Mercury | 120 Manchester Place, Newark, NJ 07104-1704 | Newark Public Schools, 2 Cedar Street, Newark NJ 07102-3051 | Public Schools | Commercial Operation | 0.51048 | One Satcon PowerGate Plus PVS-375, 8 ProHarvest HiQ inverters; 1,440 Sunpower PL-SUN-SPR-305-U, 264 Suntech STP270-24/VB-1 panels
Camden (NWK) | Newark Public Schools |  | 971 | ALM | 281 & 321 Camden Street Newark, New Jersey 07103 | Newark Public Schools, 2 Cedar Street, Newark NJ 07102-3051 | Public Schools | Commercial Operation | 0.91 | 101 ProHarvest HiQ Inverters; 3,264 ET Solar ET-P672280 panels
New Central HS | Newark Public Schools |  | 495 | LB Electric | 246 18th Ave, Newark, NJ 07108 | Newark Public Schools, 2 Cedar Street, Newark NJ 07102-3051 | Public Schools | Commercial Operation | 0.50139 | 58 ProHarvest HiQ inverters; 1,857 Suntech STP270-24/VB-1 panels
Segment 2
Pole-Attached | PSE&G |  | N/A | Riggs-Distler | Various | 80 Park Plaza, Newark, NJ 07102 | Utility | Commercial Operation | 35.7237 | Suntech STP200-18/UB-1, STP205-18/UD, STP210-18/UB-1, STP215-20/WD, STP220-20/WD, STP225-20/WD, Trina Solar TSM-220PA05, TSM-225PA05, TSM-235PA05, TSM-240PA05
Notes:
"Cost per Project" corresponds to projects that have been placed in service.
"NPV of 20 Year Lease Cost" is derived using an annual discount rate of 5.07%
Regarding Segment 2 (Pole-attached): Riggs Distler is the installation contractor, not an EPC contractor
"Cost per Project" includes AFUDC

## Website Posting 4-20-2011 (hidden)
PSE&G Solar 4 AllTM Program Centralized Solar Program Capacity
Site | EPC Contractor | System Size MW-dc | Status as of 4-20-2011
Segment 1a
PSE&G Linden Solar Farm | ASP | 3.1939 | In Service
PSE&G Yardville Solar Farm | ACE | 4.3024 | In Service
PSE&G Silver Lake Solar Farm | JFC | 2.0176 | In Service
PSE&G Trenton Solar Farm | SunEdison | 1.2641 | In Service
PSE&G Central Division HQ Roof Solar | Solis (Solyndra) | 0.91628 | In Service
PSE&G Edison Training Center Roof, Land & Car Port Solar | Henkle & McCoy | 0.7119 | In Service
PSE&G Thorofare Solar Farm |  | 0.859 | Engineering
PSE&G Hackensack Solar Farm |  | 1.13 | Engineering
PSE&G Metro HQ; BIPV & Car Port Solar |  | 1.381 | Engineering
PSE&G Moorestown HQ; BIPV & Car Port Solar |  | 1.3 | Engineering
TOTAL |  | 17.0761
Segment 1b
WEA Roof Solar (Bayonne) | ASP | 1.7464 | In Service
Rider University Solar Farm | Alteris | 0.7392 | Permitting
Matrix (Stults Road, Dayton) Roof Solar | Pro-Tech | 3 | In Construction
Flat Rate Moving Roof Solar | Mercury | 1.1033 | Engineering
TOTAL |  | 6.5889
Segment 1c
Matrix Bldg A (Perth Amboy) Roof Solar | enXco | 1.688 | In Service
Matrix Bldg B (Perth Amboy) Roof Solar | enXco | 1.1707 | In Service
Newark Public Schools Barringer HS Roof Solar | Mercury | 0.644 | In Service
Newark Public Schools Park Avenue Elementary School Roof and Car Port Solar | Mercury | 0.51312 | In Service
Newark Public Schools Camden Street Schools Roof and Car Port Solar | ALM | 0.91 | 0.7 MW in service, remainder under construction
Newark Public Schools New Central HS Roof Solar | LB Electric/EnterSolar | 0.50139 | In Service
TOTAL (under development) |  | 5.4272
Combined
TOTAL* |  | 29.0921
* The remaining capacity under the 40 MW program in Segment 1 is in negotiation
Note on D6: A Powers: System size reduction based on as-built, 2/14/11

## S4A_Capacity Schedule (hidden)
Site | EPC Contractor | System Size MW-dc | System Size (MW-ac) | WMPA Capacity MW -AC) | Production (mWh/yr) | Estimated Commercial Operation Date | Address | PJM Queue # | WMPA Executed | Locational Deliverability Area (LDA) PS- NORTH / REST OF PS
Segment 1a
Linden | #REF! | #REF! | #REF! |  | #REF! | 2010-12-01 | South Wood Avenue, Linden, NJ | V1-030 | Yes
Yardville | #REF! | #REF! | #REF! |  | #REF! | 2010-12-01 | Broad Street, Hamilton, NJ | V1-030 | Yes | REST OF PS
Silver Lake | #REF! | #REF! | #REF! |  | #REF! | 2010-11-01 | 410 Silver Lake Avenue, Edison, NJ | V1-030 | Yes | REST OF PS
Trenton | #REF! | #REF! | #REF! |  | #REF! | 2010-10-01 | 500-520 Brunswick Avenue, Trenton, NJ | V1-030 | Yes | REST OF PS
Central HQ | #REF! | #REF! | #REF! |  | #REF! | 2010-12-01 | 472 Weston Canal Road, Franklin, NJ 08873 | W2-035 | No
Metro/Clifton | #REF! | #REF! | #REF! |  | #REF! | 2010-12-01 |  | Project Proposal Review
Edison Training | #REF! | #REF! | #REF! |  | #REF! | 2010-12-01 | 234 Pierson Avenue, Edison, NJ 08837 | Pending Submittal to PJM | No
#REF! | #REF! | #REF! | #REF! |  | #REF! | 2010-12-01 |  | Project Proposal Review
S. DivHQ Moorestown | #REF! | #REF! | #REF! |  | #REF! | 2010-12-01 |  | Project Proposal Review
#REF! | #REF! | #REF! | #REF! |  | #REF! | 2010-12-01 |  | Project Dropped
#REF!
Total |  | #REF! | #REF!
Segment 1b
#REF! | #REF! | #REF! | #REF! |  | #REF! | 2011-02-01 | 1500 John Galt Way, Burlington, NJ | Submitted - Withdrawn | No
#REF! | #REF! | #REF! | #REF! |  | #REF! | 2011-02-01 | 1100 John Galt Way, Burlington, NJ | Project Dropped
#REF! | #REF! | #REF! | #REF! | 1.741 | #REF! | 2010-12-01 | 1500 Rahway Avenue, Avenel, NJ | W1-100 | No
CPP Bayonne | #REF! | #REF! | #REF! | 1.4 | #REF! | 2010-12-01 | 30-100 Pulaski Street, Bayonne, NJ | W1-101 | No
Rider | #REF! | #REF! | #REF! |  | #REF! | 2011-06-01 | Rider University 2083 Lawrenceville Rd. Lawrenceville, NJ 08648 | Project on Hold
#REF! | #REF! | #REF! | #REF! | 1.282 | #REF! | 2011-01-01 | 25 East Park Dr, Westampton, NJ 08060 | W1-099 | No
#REF! | #REF! | #REF! | #REF! | 0.965 | #REF! | 2011-01-01 | 84 Stemmers Lane, Westampton, NJ 08060 | W1-098 | No
Food Bank | #REF! |  |  |  | #REF! | 2010-12-01 | 99 Evergreen St, Newark, NJ 07102 | Project Dropped
Vincetown | #REF! | #REF! | #REF! | 1.9 |  | 2011-02-01 | 214 Buddtown Road, Vincetown, NJ | Submitted - Withdrawn W1-102 | No
Roosevelt | #REF! | #REF! | #REF! |  |  | 2010-12-01 |  | Project on Hold
Total |  | #REF! | #REF!
Segment 1c
Matrix Bldg A & B | #REF! | #REF! | #REF! | 2.308 | #REF! | 2010-12-01 | 1000 and 1050 Amboy Ave, Perth Amboy, NJ | V3-069 | Yes
Barringer | #REF! | #REF! | #REF! | 0.549 | #REF! | 2010-09-01 | 90 Parker St, Newark, NJ 07104 | V3-065 | Yes | PS NORTH
Park | #REF! | #REF! | #REF! | 0.432 | #REF! | 2010-10-01 | 120 Manchester Place, Newark, NJ 07104-1704 | V3-066 | Yes | PS NORTH
Camden (NWK) | #REF! | #REF! | #REF! | 0.773 | #REF! | 2010-10-01 | 281 Camden Street Newark, New Jersey 07103 | V3-067 | Yes | PS NORTH
New Central HS | #REF! | #REF! | #REF! | 0.425 | #REF! | 2010-09-01 | 246 18th Ave, Newark, NJ 07108 | V3-068 | Yes | PS NORTH
Total |  | #REF! | #REF!
Segment 2
Pole Attached Solar |  | 40 | 30.8 |  |  | 2009 through 2012 |  | V1-030 | Yes
Notes:
Where possible, values reported are linked to main tab.
Other values are calculated based on assumed DC to AC factors for projects with pending contracts.
Values should be checked for accuracy .
AG 3/10/10
Note on D19: Grisolia, Albert: Not linked to main tab For PJM submittal, .95 dc to ac factor used for capacity.

## Site Equipment (hidden)
Solar Facility Equipment / Manufacturer's List
| Inverters |  |  | PV Module |  | Mounting / Racking |  | Combiner Boxes |  | Re-Combiner Boxes
Site | Mfr. | Model(s) | Qty. | Mfr. | Model(s) | Mfr. | Model | Mfr. | Model(s) | Mfr. | Model
Segment 1a
Linden | SMA | Sunny Central 500-HE-US | 6 | Suntech | STP280-24/Vd | Advanced Solar | Solstice Mounting System
Yardville | Advanced Energy | Solaron Inverter 250kW, 500 kW | 8 | Suntech | STP 275-24/Vb-1, STP 280-24/Vb-1 | Unirac | ISYS Ground Mount System
Silver Lake | SMA | Sunny Central SC 250U, SC 500U | 4 | Sharp | ND-224UC1, ND-U235F1 | Advanced Solar | Solstice Mounting System
Trenton | Satcon | PowerGate Plus 135 kW, 500 kW | 3 | Yingli Solar | YL 230 Pb-2/1650x990 Series | Sun Edison | RBT mounting system | SolarBOS | CS150-24-15-N3 | N/A | N/A
Central | Satcon | PowerGate Plus 250 kW | 3 | Solyndra | SL-001-182 | N/A | N/A | Amtec Solar | Prominence 24 | Amtec Solar | Equinox 2000
|  |  |  | Solar World | Sunmodule 245W | Unirac | TLH High Profile Tilt Legs
Edison | Satcon | PowerGate Plus 135 kW, 500 kW | 2 | Gloria Solar | GSM6-225D-E1 | Solar Flexrack | Ground Mount 2x7
Segment 1b
Avenel | SMA | 500U | 4 | Hyundai | 227W, 230 W | Advanced Solar | Solstice Mounting System
Bayonne | SMA | 500U | 3 | Trina | 220 W | Advanced Solar | Solstice Mounting System
Standard Register | Satcon | PowerGate 500kw, PowerGate 50kw | 2 | Gloria Solar | GSM6-230D-E1 | SunLink | Photovoltaic (PV) Module Mounting System (MMS)
Don | Satcon | PowerGate 500kw, PowerGate 375kw | 2 | Gloria Solar | GSM6-225D-E1 | SunLink | Photovoltaic (PV) Module Mounting System (MMS)
Matrix | Advanced Energy | Solaran 500 kW | 5 | SunModule | SW-245 | SunLink | RMS | Shoals Technologies
Rider | Advanced Energy | 333.33 kW Inverter Solaron 333 | 2 | Suntech | STP280-24/Vd
Segment 1c
Matrix Bldg A | SMA | Sunny Central SC 250U, SC 500U | 3 | Suntech | STP280-24/Vd | SunLink |  | SolarBOS | CS150-24-15-N3 | Amtec Solar | Equinox 750
Matrix Bldg B | SMA | Sunny Central SC 250U, SC 500U | 2 | Suntech | STP280-24/Vd | SunLink |  | SolarBOS | CS150-24-15-N3 | Amtec Solar | Equinox 750
Barringer | Satcon | PowerGate Plus 135 kW, 250 kW | 3 | Suntech | STP280-24/Vb-1 | SunLink | Photovoltaic (PV) Module Mounting System (MMS) | Amtec Solar | Prominence 24 | N/A | N/A
Park | Satcon | PowerGate Plus 75 kW, 100 kW, 375 kW | 3 | Suntech | STP280-24/Vb-1 | Unirac (Raised Solar) | Solar Mount HD | Amtec Solar | Prominence 24, Prominence 36, Prominence 52 | N/A | N/A
|  |  |  | SunPower Corporation | 305 Solar Panel | Sunpower (Roof Mount) | Power Guard w/Light Guard |  |  | N/A | N/A
Camden | Advanced Energy | 500 kW Inverter Solaron 500, 333.33 kW Inverter Solaron 333 | 2 | ET Solar Group Limited | ET-P672280 | Sunlink
New Central | Satcon | PowerGate Plus 100kW | 2 | Suntech | STP 270-24/Vb-1 | Sunlink |  | SolarBOS | CSM1-08-15-4XF | N/A | N/A
| Satcon | Solstice 100kw | 3
Source: URS document prepared for O&M SOW 12/15/10

## WMPAs (hidden)
Segment 1b
Segment | Solar Developer | Site Name | Location | Size MW-dc | Size MW-ac | Configuration | Distribution Information | 20% dc | 20% ac | WMPA Attachment N Submitted | PJM Queue # | PJM / PSE&G Scoping Meeting Date | Circuit | Transmission | Planned Date Of Commercial Operation | Application Fee (Small Gen <2MW 1,2, or 3rd Month Queue) | Application Fee (Small Gen 3rd Month Queue $200 / MW AC) | Total Fee | PSE&G / PSE&G Interconnection Agreement (IA) executed | WMPA Received back with all Signatures
1A | ASP | Linden | South Wood Avenue, Linden, NJ | #REF! | #REF! | Ground |  |  |  | 2009-04-27 | V1-030 | [7 empty] | signed PS & PS 12/22/10
1A | ACE | Yardville | Broad Street, Hamilton, NJ | #REF! | #REF! | Ground |  |  |  | 2009-04-27 | V1-030 | [7 empty] | signed PS & PS 12/22/10
1A | JFC | Silver Lake | 410 Silver Lake Avenue, Edison, NJ | #REF! | #REF! | Ground |  |  |  | 2009-04-27 | V1-030 | [7 empty] | signed PS & PS 12/22/10
1A | SunEdison | Trenton | 500-520 Brunswick Avenue, Trenton, NJ 08638 | #REF! | #REF! | Ground |  |  |  | 2009-04-27 | V1-030 | [7 empty] | Sent 9/14/10 to PJM
1A | Solis (Solyndra) | Central Division HQ | 472 Weston Canal Road, Somerset, NJ 08873 | 0.90804 | 0.863 | Roof | 13 kV | 0.72643 | 0.6904 | 2010-06-15 | W2-036 | 2010-07-19 |  | Polhemus Lane Substation | 2010-12-15 | 1000 | 129.45 | 1129.45 | signed PS & PS 12/22/10 | 2011-01-25
1A | Henkle & McCoy | Edison Training | 234 Pierson Avenue, Edison, NJ 08837 | 0.803 | 0.763 | Roof/Ground/Raised Array | 13 kV | 0.6424 | 0.6104 | 2010-07-16 | W2-052 | 2010-08-05 | Circuit Pierson Ave 8021 13 kV | Pierson Ave |  | 1500 | 152.6 | 1652.6 | signed PS & PS 12/22/10 | 2011-01-25
1A | SunEdison | Thorofare | Jessup Road, Thorofare, NJ 08086 | 0.859 | 0.709 | Ground | 13 kV | 0.6872 | 0.5672 |  | V1-030
1A | Gloria Solar | Metro Div HQ / Clifton Gas | 150 Circle Ave, Clifton, NJ 07011 | 0.89424 | 0.85 | Roof | 13 kV | 0.71539 | 0.68 | 2011-01-25 | W4-059 | 2011-02-14 |  |  |  | 1500 | 170 | 1670
1A | Vanguard | S. DivHQ Moorestown | 360 New Albany Road, Moorestown, NJ 08057 | 1.34 | 1.273 | Roof/Raised Array | 13 kV | 1.072 | 1.0184 | 2011-04-19 | X1-071 | 2011-05-19 | Circiut Cinnaminson 8006 13 kv | Cinnaminson 138kV | 2011-11-15 | 3000 | 254.6 | 3254.6
1A | JFC | Hackensak | 194-210 South River Street, Hackensack NJ 07601 | 1.135 | 1.078 | Ground | 13 kV | 0.908 | 0.8624 | 2011-04-20 | X1-072 | 2011-05-19 | Circiut Hackensack 4005/4013 4 kV | Bergen 138kV | 2011-11-15 | 3000 | 215.6 | 3215.6
1B | Advanced Solar Products - WEA Texas Bayonne | WEA Texas Bayonne | 30-100 Pulaski Street, Bayonne, NJ | 1.4737 | 1.4 | Roof |  | 1.1789 | 1.12 | 2010-04-23 | W1-101 | 2010-06-03 | Circuit Bayonne 8008 | Bayonne Sub 131 kV | 2010-12-01 |  |  |  | Sent 9/14/10 to PJM | 2010-10-06
1B | Pro-Tech | Matrix - Stults Rd | 45 Stults Rd, 'South Brunswick, NJ 08810 | 3 | 2.85 | Roof | 13 kV Devils Brook | 2.4 | 2.28 | 2010-10-27 | W3-124 | 2010-11-24 | Circiut Devils Brook 13 kV | Devil's Brook | 2011-04-30 | 3000 | 570 | 3570 |  | 2011-03-24
1B | Mercury | Flat Rate Moving | 99 Evergreen Ave, Newark, NJ 07114 | 1.1033 | 1.0481 | Roof |  |  |  | 2011-01-12 | W4-048 | 2011-02-07 |  |  | 2011-06-30 | 1500 | 209.63 | 1709.63
1B | Alteris | Rider | 2083 Lawrenceville Road, Lawrenceville NJ 08648 | 0.7392 | 0.70224 | Ground |  |  |  | 2011-01-21 | W4-058 | 2011-02-14 |  |  | 2011-07-31 | 1500 | 140.45 | 1640.45
1B | Sundurance | NJMC Landfill
1B | Juwi | Mill Creek | Irick Road, Westampton, NJ 08060 | 3.99 | 3.7905 | Ground |  |  |  | 2011-04-19 | X1-070 | 2011-05-19 | Circiut Levittown 8016 13 kV | Levittown 138kV | 2011-09-15 | 3000 | 758.1 | 3758.1
1B | ASP | Matrix Field
1C | enXco | Matrix Bldg | 1000 and 1050 Amboy Ave, Perth Amboy, NJ | #REF! | 2.308 | Roof | 13 kV, Woodbridge |  |  | 2009-10-30 | V3-069 | [7 empty] | Sent 8/13/10 to PJM | 2010-04-02
1C | Mercury | Barringer | 90 Parker St, Newark, NJ 07104 | #REF! | 0.549 | Roof | 4 kV, Clay Street |  |  | 2009-10-30 | V3-065 | [7 empty] | Sent 8/13/10 to PJM | 2010-04-02
1C | Mercury | Park | 120 Manchester Place, Newark, NJ 07104-1704 | #REF! | 0.432 | Roof | 13.8 kV, Cook Road |  |  | 2009-10-30 | V3-066 | [7 empty] | Sent 8/13/10 to PJM | 2010-04-02
1C | ALM | Camden (NWK) | 281 Camden Street Newark, New Jersey 07103 | #REF! | 0.773 | Roof | 4 kV, Norfolk Street |  |  | 2009-10-30 | V3-067 | [7 empty] | Sent 8/13/10 to PJM | 2010-04-02
1C | LB Electric/EnterSolar | New Central HS | 246 18th Ave, Newark, NJ 07108 | #REF! | 0.425 | Roof | 4 kV, Norfolk Street |  |  | 2009-10-30 | V3-068 | [7 empty] | Sent 8/13/10 to PJM | 2010-04-02
1B | Juwi Haines Solar - Whitesell - 1500 John Galt Way | Whitesell 1500 John Galt Way | 1500 John Galt Way, Burlington, NJ | 2000 | 1900 | Roof | 13 kV, BUS8013, 3ph, 1-awg wire (underground) | 1600 | 1520 | 04/13/2010 - Withdrawn
1B | Juwi Haines Solar - Whitesell - 1100 John Galt Way | Whitesell 1100 John Galt Way | 1100 John Galt Way, Burlington, NJ | 2000 | 1900 | Roof | 13 kV, BUS8013, 3ph, 1-awg wire (underground) | 1600 | 1520 | HOLD
1B | Alteris Renewables - Rider University 1334 | Rider University | Rider University 2083 Lawrenceville Rd. Lawrenceville, NJ 08648 | 1334 | 1267.3 | Ground | Next to substation | 1067.2 | 1013.84 | HOLD
1B | Mercury Solar - Roosevelt Paper | Roosevelt Paper | 10 Roosevelt Drive, Mt. Laurel NJ 08054 | 2000 | 1900 | Roof |  | 1600 | 1520 | HOLD
1B | ALM Vincetown | Vincetown Farm | 214 Buddtown Road, Vincetown, NJ | 2000 | 1900 | Ground | 13kV, SOH8032 | 1600 | 1520 | 6/02/10 - Withdrawn | *W1-102
1B | Gloria Spire - Dolan Contractors- "Don" Bldg | Dolan - Don Bldg | 84 Stemmers Lane, Westampton, NJ 08060 | 1.0157 | 0.96491 | Roof | 13 kV, LEV8009, 3ph (underground) | 0.81256 | 0.77193 | 2010-04-23 | W1-098 | 2010-06-03 | Circuit Levittown 8014 | Levittown Sub 138 kV | 2011-01-01 |  |  |  | Sent 9/14/10 to PJM | 2010-10-06
1B | Advanced Solar Products - Avenel | 1500 Rahway - Avenel | 1500 Rahway Avenue, Avenel, NJ | 1.8326 | 1.741 | Roof | 13 kV, MIN8011 | 1.4661 | 1.3928 | 2010-04-23 | W1-100 | 2010-06-03 | Circuit Minue 8023 | Minue Street Sub 230 kV | 2010-12-01 |  |  |  | Sent 9/14/10 to PJM | 2010-10-06
1B | Gloria Spire - Dolan Contractors- Std Register Bldg | Dolan - Standard Register Bldg | 25 East Park Dr, Westampton, NJ 08060 | 1.3496 | 1.2821 | Roof | 13 kV, LEV8013, 3ph (underground) | 1.0797 | 1.0257 | 2010-04-23 | W1-099 | 2010-06-03 | Circuit Levittown 8014 | Levittown Sub 138 kV | 2011-01-01 |  |  |  | Sent 9/14/10 to PJM | 2010-10-06
1B | Techta | 234 Moonachie Corp | 234 Moonachie Road, Moonachie, NJ 07074 | 1.3275 | 1.2611 | Roof | 13kV, RFL 8014 and RFL 8042 | 1.062 | 1.0089 | 2010-07-30 | W3-004 | 2010-10-05 |  |  | 2011-01-15 | 500 | 126.11 | 626.11
Total
Note on F3: Grisolia, Albert: .95 DC to AC factor used for submitting estimated MAX AC kW for WMPA submittal. PSE&G to adjust system size downward prior to executing WMPA.
Note on Q3: Grisolia, Albert: Note on 4/20/11 PJM notified PSE&G that rates for small generators which are both capacity & energy resources should be based on Manual 14a, Table 3-1 and not Table 3-2 as perviously instructed.
Note on E8: Grisolia, Albert: Starting System size for submittal to PJM.
Note on E9: Grisolia, Albert: Starting system size for submittal to PJM.
Note on E10: Grisolia, Albert: Starting system size for submittal to PJM. USING DC Sys size as of 4/21/11 of 0.859 MW DC and .825 factor = 0.709 MW AC is system size covered under V1-30. PS can do cap mod upwards if needed in future.
Note on E11: Grisolia, Albert: Starting system size for submittal to PJM.
Note on E12: Grisolia, Albert: System size submitted for WMPA is on high side - final size not know at time of submittal to pjm
Note on E15: Grisolia, Albert: Starting system size for pjm WMPA submittal.
Note on E16: Grisolia, Albert: Starting system size for pjm WMPA submittal
Note on E17: Grisolia, Albert: Starting system size for submittal to PJM.
Note on E18: Grisolia, Albert: Starting system size for submittal to PJM.
Note on E37: Grisolia, Albert: Starting system size for PJM WMPA submittal.
Note on E38: Grisolia, Albert: Starting System size for pjm WMPA submittal
Note on E39: Grisolia, Albert: Starting system size for pjm WMPA submittal.
Note on E40: Grisolia, Albert: Starting system size for pjm WMPA submittal

## Project Contacts (hidden)
PSE&G Solar 4 All Program Contractor Contacts
Site | Bidder | Contact | Phone | Cell | Email
Segment 1A
Cox's Corner
Central Gas Edison | J. Fletcher Creamer & Son Inc. | Dan Urban | 908-986-5729 | 609-868-3124 | durban@jfcson.com
Brunswick Ave | Sun Edison | Franny Yuhas (sales) | 443-909-7200 | 410-375-9420 | fyuhas@sunedison.com
|  | Mike Belko (ops director) |  |  | mbelko@sunedison.com
Yardville | American Capital Energy, Inc. | Pat McDonald | 914-834-2863 | 914-715-3966 | pmcdonald@americancapitalenergy.com
Linden SNG | Advanced Solar Products | Ed Seliga | 609-466-4495 | 732-672-7490 | ed@advancedsolarproducts.com
|  | Lyle Rawlings |  |  | lyle@advancedsolarproducts.com
Segment 1C
Science Park
Matrix | enXco Service Corporation | John Moran |  | 917-442-4574 | JMoran@enxco.com
Barringer | Mercury Solar Systems | Matt Effler | 914-637-9700 | 914-275-2831 | meffler@mercurysolarsystems.com
Park | Mercury Solar Systems | Matt Effler | 914-637-9700 | 914-275-2831 | meffler@mercurysolarsystems.com
Camden | A.L.M. Electric Co., Inc | Sham Ramnarain | 973-588-7307 | 201-341-3817 | sramnarain@greensource2020.com
St Vincent
New Central | LB Electrical | Leon Baptiste | 973-571-2200 | 973-462-7623 | lbaptiste@lbelectricco.com
Louis MuNoz | May Sie Enterprise Corp. | Aaron Gibson | 732.247.0168 | 732.687.1015 | onasm@msn.com
Segment 1B
Dolan Buildings (2) | Gloria Solar | Pete Farlakas | 973-860-1860 | 860-227-2761 | peter.farlekas@us.gloriasolar.com
Whitesell | Juwi | Mike Martin | 303-440-7430 | 720-320-4003 | mmartin@juwisolar.com
Flat Rate Moving | Mercury | Matt Effler | 914-637-9700 | 914-275-2831 | meffler@mercurysolarsystems.com
Rider University | Alteris | Andy Kern | 732-308-0304 | 609-529-8826 | akern@alterisinc.com
Avenel | Advanced Solar Products | Scott Schultz | 908-751-5818 | 732-672-7490 | scott@advancedsolarproducts.com
|  | Lyle Rawlings |  |  | lyle@advancedsolarproducts.com
Bayonne | Advanced Solar Products | Scott Schultz | 908-751-5818 | 732-672-7490 | scott@advancedsolarproducts.com
|  | Lyle Rawlings |  |  | lyle@advancedsolarproducts.com

## Plant Insurance Info (hidden)
Solar Plant Insurance Information
Segment 1A - PSE&G Owned Property
| Solar Plant Name: | Linden Solar Farm
| Location: | South Wood Avenue, Linden, NJ
| System Size (watts-dc): | 3193930
| Solar Plant Value: | 15899138.6138
| Solar Plant Name: | Silver Lake Solar Farm
| Location: | 410 Silver Lake Avenue, Edison, NJ
| System Size (watts-dc): | 2017596
| Solar Plant Value: | 10853833.7291
| Solar Plant Name: | Trenton Solar Farm
| Location: | 500-520 Brunswick Avenue, Trenton, NJ
| System Size (watts-dc): | 1264080
| Solar Plant Value: | 6243262.4709
| Solar Plant Name: | Central Division Headquarters
| Location: | 472 Weston Canal Road, Franklin, NJ 08873
| System Size (watts-dc): | 921500
| Solar Plant Value: | 6468602.0225
| Solar Plant Name: | Edison Training Center
| Location: | 234 Pierson Avenue, Edison, NJ 08837
| System Size (watts-dc): | 711900
| Solar Plant Value: | 4318504.7024
Segment 1B - Third Party Owned Property
| Solar Plant Name: | WEA Bayonne Solar
| Location: | 30-100 Pulaski Street, Bayonne, NJ
| System Size (watts-dc): | 1746360
| Solar Plant Value: | 8301476.1757
| Solar Plant Name: | Matrix - 45 Stultz Rd
| Location: | 45 Stultz Rd, South Brunswick, NJ
| System Size (watts-dc): | 2980740
| Solar Plant Value: | 12760274.6937
Segment 1C - Third Party Owned Property (UEZ)
| Solar Plant Name: | New Central High School
| Location: | 246 18th Ave, Newark, NJ 07108
| System Size (watts-dc): | 501390
| Solar Plant Value: | 2842956.5964
| Solar Plant Name: | Barringer High School
| Location: | 90 Parker St, Newark, NJ 07104
| System Size (watts-dc): | 648800
| Solar Plant Value: | 3256690.3329
| Solar Plant Name: | Park Elementary School
| Location: | 120 Manchester Place, Newark, NJ 07104-1704
| System Size (watts-dc): | 513120
| Solar Plant Value: | 3341209.8257

## AS Builts (hidden)
Solar 4 All |  |  |  | AS-BUILTS/Final Doc. Inventory | AS-BUILTS ON DISC | Hard Copies
Segment 1 A
J Fletcher Creamer | 1 | 10187541.97 | #DIV/0! | Silver Lake - contract date 12/24/9 (Contract Finish 11/23/10) |  | O & M manual
NVT Licenses (SunEd) | 2 | watts | #VALUE! | Trenton - contract date 12/10/9 (Contract Finish 9/20/10) | Original from EPC, 2 copies, copy on M-drive | O & M manual
Contract Amt (per CO_2) | 3 | 21597379.78 | #DIV/0! | 4500551895
Advanced Solar Products | 4 | 14069656.33 | #VALUE! | Linden - contract date 12/29/9 (Contract Finish 2/10/11) | Original from EPC, 2 copies, copy on M-drive | O&M Manual, QA/QC Docs.
Solis | 5 | 6230415.37 | #DIV/0! | Central HQ - contract date (may 2010) |  | Project Documents
Henkel & McCoy | 6 | 4212094.05 | #DIV/0! | EDISON TRAINING CTR |  | O & M manual, QA Testing
SunEdison | 7 | 3490000 | #DIV/0! | THOROFARE
TBD | 8 | 4229000 | #DIV/0! | T-Line Right of Way
Gloria Solar | 9 | 7707836 | #DIV/0! | METRO HEADQUATERS
Vanguard | 10 | 7319000 | #DIV/0! | S. Division/Moorestown - contract date ??
Segment 1 B
GLORIA SOLAR | 1 | 588557.3 | #VALUE! | Dolan - Standard Register Bldg (Contract Finish 12/22/10) | project cancelled
GLORIA SOLAR | 2 | 445574.3 | #VALUE! | Dolan - Don Bldg (Contract Finish 12/22/10) | project cancelled
ADVANCED SOLAR PRODUCTS | 3 | 11833915.2 | #DIV/0! | MATRIX FIELD
ADVANCED SOLAR PRODUCTS | 4 | 7847511.73 | #VALUE! | WEA - Bayonne | Original from EPC, 2 copies, copy on M-drive | O&M Manual, QA/QC Docs.
PRO-TECH | 5 | 12092641.51 | #DIV/0! | MATRIX
ALTERIS RENEWABLES | 6 | 3422496 | #DIV/0! | RIDER UNIVERSITY
Juwi | 7 | 0 | #DIV/0! | MILLS CREEK
TBD | 8 | 2766750 | #DIV/0! | TBD
Project Total | 9 | 3001000 | #DIV/0! | 0
MERCURY SOLAR | 10 | 4615663 | #DIV/0! | FLAT RATE MOVING
Segment 1 C
Mercury Solar Systems | 1 | 3175806.05 | #DIV/0! | Park - contract date 2/15/10 (Contract Finish 9/16/10) |  | O & M manual, Installation manual
Mercury Solar Systems | 2 | 3061598 | #DIV/0! | Barringer - contract date 2/15/10 (Contract Finish 8/25/10) |  | O & M manual, Installation manual
LB Electric | 3 | 2691185 | #VALUE! | New Central - contract date 2/23/10 (Contract Finish 10/12/10) | Original from EPC, 2 copies, copy on M-drive | Close out documents
A.L.M. Electric | 4 | 5497356.47 | #DIV/0! | Camden - contract date 2/23/10 (Contract Finish 12/17/10)
enXco | 5 | 14379345.16 | #DIV/0! | Matrix Bldg - contract date (Contract Finish ??)
IN SERVICE - Investment $'s
Segment 1 A
Segment 1 B
Total 1A & 1B
Segment 1 C
Total 1C
IN SERVICE - Investment $'s by Asset Class
Segment 1A
|  |  | 93.73% | Panels
|  |  | 5.139% | Inverters
|  |  | 0.3295% | Communication Equipment
Meters
|  |  | 0.7985% | Other (InterConnection)
|  |  | 100% | Total Segment 1A
Segment 1b
|  |  | 91.9% | Panels
|  |  | 7.804% | Inverters
|  |  | 0.2927% | Communication Equipment
Meters
Other (InterConnection)
|  |  | 100% | Total Segment 1b
Segment 1c
|  |  | 89.82% | Panels
|  |  | 8.531% | Inverters
|  |  | 1.648% | Communication Equipment
Meters
Other (InterConnection)
|  |  | 100% | Total Segment 1c
Combined 1a & 1b
Panels
Inverters
Communication Equipment
Meters
Other (InterConnection)
Total Segment 1a+b
as-built final docs. Inventory
last tab, Forecast

## Monthly & YTD Updates
Solar 4 All Monthly Activity Report - February 2025
February 2025 Monthly Update
| Segment | Energy Produced (MWh AC) | Net Energy Sales ($) | SREC's Sold | SREC Revenue ($) | Capacity Sold (MW-days) | Net Capacity Sales ($) | Business Interruption Insurance Recovery ($) | Investment ($) | Program Expenses ($) | Projects Completed / Seg 2 Panels Installed | MW Installed | Pole-attached Units Communicating
| Segment 1a | 1221.4784 | 47556.1777 |  |  | 0 | 0 | 0 | 0 | 38233.57 | 0 | 0
| Segment 1b | 1323.4822 | 51870.6734 |  |  | 0 | 0 | 0 | 37800 | 138935.06 | 0 | 0
| Segment 1c | 171.8986 | 6557.6843 |  |  | 0 | 0 | 0 | 0 | 38649.33 | 0 | 0
| Segment 2 | 2347.0847 | 92996.6876 |  |  | 0 | 0 | 0 | 3856 | 411810.41 | 0 | 0 | 151861
| Program Total | 5063.9439 | 198981.2229 | 0 | 0 | 0 | 0 | 0 | 41656 | 627628.37 | 0 | 0
Solar 4 All Year-to-Date Activity Report
Year-to-Date Update through February 2025
| Segment | Energy Produced (MWh AC) | Net Energy Sales ($) | SREC's Sold | SREC Revenue ($) | Capacity Sold (MW-days) | Net Capacity Sales ($) | Business Interruption Insurance Recovery ($) | Investment ($) | Program Expenses ($) | Projects Completed / Seg 2 Panels Installed | MW Installed
| Segment 1a | 2190.3091 | 98396.7844 |  |  | 0 | 0 | 0 | 0 | 136253.38 | 0 | 0
| Segment 1b | 2451.5975 | 111705.2734 |  |  | 0 | 0 | 0 | 37800 | 244065.73 | 0 | 0
| Segment 1c | 293.5381 | 12727.9127 |  |  | 0 | 0 | 0 | 0 | 174608.29 | 0 | 0
| Segment 2 | 4577.6706 | 214076.9264 |  |  | 0 | 0 | 0 | 40703.25 | 870933.12 | 0 | 0
| YTD Program Total | 9513.1153 | 436906.8968 | 0 | 0 | 0 | 0 | 0 | 78503.25 | 1425860.52 | 0 | 0
Solar 4 All Program-to-Date Activity Report
Program-to-Date through February 2025
| Segment | Energy Produced (MWh AC) | Net Energy Sales ($) | SREC's Sold | SREC Revenue ($) | Capacity Sold (MW-days) | Net Capacity Sales ($) | Business Interruption Insurance Recovery ($) | Investment ($) | Program Expenses ($) | Projects Completed / Seg 2 Panels Installed | MW Installed
| Segment 1a | 257741.2078 | 8923427.5126 | 255123 | 55798062.9103 | 15316.7 | 2286339.3985 | 320277 | 101891694.23 | 11452817.46 | 10 | 16
| Segment 1b | 294793.2269 | 10893062.1595 | 290957 | 61620214.4382 | 16886.7 | 2807758.368 | 457127.23 | 85478643.07 | 29087501.57 | 8 | 18.51
| Segment 1c | 78969.2031 | 2746963.8138 | 79634 | 17366668.501 | 5958.6 | 812967.0579 | 0 | 35916067.93 | 10737496.44 | 6 | 5.4
| Segment 2 | 486477.3964 | 19376360.1579 | 497631 | 109805468.7577 | 33520 | 5163194.4275 | 0 | 286141632.11 | 52418940.54 | 161248 | 35.7237
| Program-to-date Total | 1117981.0342 | 41939813.6437 | 1123345 | 244590414.6072 | 71682 | 11070259.2519 | 777404.23 | 509428037.34 | 103696756.01 | 161272 | 75.6337
Notes:
1) "SREC's Sold" and "SREC Revenue" includes vintage year 2011 through 2024 SRECs
2) Monthly "Pole-attached Units Installed" & "Pole-attached MW Installed" are preliminary estimates and subject to change. Adjustments to prior months will be reflected in YTD values.
Capacity specified in certain previously filed capacity reports represented gross installed capacity. The values shown in the table above account for net installed capacity (total installs minus total removals).
3) "Pole Attached Units Communicating" represents the average, daily number of panels that communicated during the month.
4) The columns "Energy Produced" and "SRECs Sold" do not sync because of the timing of SREC auctions, through which SRECs are sold.
5) Business interruption insurance recovery received for lost energy sales and SREC sales due to Superstorm Sandy

## Written Summary
Total S4A Fleet Performance:
February weather conditions were unfavorable for solar production.
Seg2 (Pole Attached Solar):
· Ongoing maintenance of existing installations continues.

## Seg 2 - Panels by Muni
PSE&G Pole-Attached -- Summary by Municipality -- February 2025
| Total | Total kWdc
Allentown Boro | 55 | 11.83
Audubon Boro | 519 | 110.78
Audubon Park Boro | 48 | 9.95
Barrington Boro | 382 | 82.34
Bayonne City | 1824 | 416.06
Belleville Twp | 900 | 209.43
Bellmawr Boro | 1119 | 240.04
Bergenfield Boro | 464 | 104.68
Berkeley Heights Twp | 5 | 1.2
Beverly City | 276 | 58.03
Bloomfield Twp | 1117 | 263.48
Bogota Boro | 209 | 49.22
Bordentown City | 71 | 15.17
Bordentown Twp | 930 | 200.16
Bound Brook Boro | 445 | 101.47
Branchburg Twp | 25 | 6
Bridgewater Twp | 1903 | 426.93
Brooklawn Boro | 251 | 52.9
Burlington City | 1335 | 283.48
Burlington Twp | 1379 | 288.64
Caldwell Boro | 205 | 48.42
Camden City | 6265 | 1362.22
Carlstadt Boro | 732 | 170.77
Carteret Boro | 1827 | 391.6
Cedar Grove Twp | 584 | 137.03
Cherry Hill Twp | 3487 | 744.19
Chesterfield Twp | 433 | 93.22
Cinnaminson Twp | 1377 | 288.85
Clark Twp | 751 | 166.41
Cliffside Park Boro | 300 | 70.92
Clifton City | 3316 | 772.57
Collingswood Boro | 731 | 157.13
Cranbury Twp | 341 | 74.36
Cranford Twp | 744 | 166.56
Cresskill Boro | 2 | 0.44
Delanco Twp | 327 | 67.76
Delran Twp | 740 | 154.3
Deptford Twp | 1815 | 393.1
Dumont Boro | 464 | 103.77
Dunellen Boro | 335 | 74.6
East Amwell Twp | 2 | 0.41
East Brunswick Twp | 2413 | 529.4
East Newark Boro | 37 | 8.22
East Orange City | 1420 | 335.04
East Rutherford Boro | 484 | 113.17
Eastampton Twp | 327 | 68.26
Edgewater Boro | 120 | 28.01
Edgewater Park Twp | 556 | 114.75
Edison Twp | 5503 | 1194.53
Elizabeth City | 3745 | 815.77
Elizabeth City | 292 | 64.83
Elmwood Park Boro | 791 | 181.61
Emerson Boro | 286 | 63.86
Englewood City | 900 | 207.48
Englewood Cliffs Boro | 268 | 63.52
Essex Fells Twp | 65 | 15.26
Evesham Twp | 863 | 183.12
Ewing Twp | 2652 | 570.13
Fair Lawn Boro | 1098 | 245.12
Fairfield Twp Ess | 1147 | 267.82
Fairview Boro | 268 | 62.57
Fanwood Boro | 275 | 63.14
Fieldsboro Boro | 69 | 15.27
Florence Twp | 980 | 206.65
Fort Lee Boro | 699 | 164.65
Franklin Twp Som | 3238 | 698.44
Franklin Twp Som | 98 | 22.16
Garfield City | 626 | 145.85
Garwood Boro | 247 | 55.89
Glen Ridge Boro | 18 | 4.3
Glen Rock Boro | 160 | 36.09
Gloucester City | 992 | 212.87
Gloucester Twp | 1790 | 385.25
Green Brook Twp | 346 | 78.03
Guttenberg Town | 25 | 5.97
Hackensack City | 1498 | 346.93
Haddon Heights Boro | 372 | 82.09
Haddon Twp | 988 | 211.51
Haddonfield Boro | 166 | 37.4
Hainesport Twp | 567 | 121.17
Haledon Boro | 124 | 27.88
Hamilton Twp Mer | 7040 | 1513.27
Harrison Town | 339 | 76.59
Hasbrouck Heights | 385 | 90.06
Haworth Boro | 41 | 9.38
Hawthorne Boro | 481 | 106.51
Highland Park Boro | 577 | 126.91
Hillsborough Twp | 1764 | 387.5
Hillsborough Twp | 1 | 0.2
Hillsdale Boro | 35 | 8.19
Hillside Twp | 730 | 160.05
Hillside Twp | 3 | 0.62
Hi-Nella Boro | 51 | 10.92
Hoboken City | 323 | 76.21
Hohokus Boro | 41 | 9.09
Hopewell Boro | 76 | 17.83
Hopewell Twp Mer | 516 | 114.03
Irvington Town | 1183 | 263.12
Jersey City | 4521 | 1027.35
Kearny Town | 1 | 0.2
Kearny Town | 1431 | 320.79
Kenilworth Boro | 378 | 83.34
Lawnside Boro | 270 | 58.19
Lawrence Twp Mer | 1577 | 340.46
Leonia Boro | 186 | 43.49
Lincoln Park Boro | 6 | 1.39
Linden City | 2979 | 635.48
Little Falls Twp | 455 | 105.26
Little Ferry Boro | 493 | 113.83
Livingston Twp | 2 | 0.46
Livingston Twp | 495 | 116.49
Lodi Boro | 680 | 157.83
Lumberton Twp | 487 | 101.86
Lyndhurst Twp | 914 | 213.9
Magnolia Boro | 439 | 97.54
Mansfield Twp Bur | 615 | 127.35
Manville Boro | 641 | 144.71
Maple Shade Twp | 1342 | 282.64
Maplewood Twp | 393 | 88.47
Maywood Boro | 227 | 53.49
Medford Lakes Boro | 32 | 6.75
Medford Twp | 668 | 139.53
Merchantville Boro | 217 | 46.43
Metuchen Boro | 629 | 138.48
Middlesex Boro | 980 | 218.89
Midland Park Boro | 81 | 19.11
Millburn Twp | 9 | 2.13
Millstone Boro | 38 | 8.32
Milltown Boro | 12 | 2.79
Monroe Twp Mid | 3 | 0.63
Montclair Twp | 779 | 185.39
Montgomery Twp | 20 | 4.46
Montgomery Twp | 812 | 178.55
Moonachie Boro | 394 | 89.84
Moorestown Twp | 1178 | 251.45
Mount Ephraim Boro | 351 | 74.58
Mount Holly Twp | 590 | 124.71
Mount Laurel Twp | 1187 | 252.27
Mountainside Boro | 315 | 72.4
National Park Boro | 357 | 77.95
New Brunswick City | 2011 | 431.74
New Milford Boro | 310 | 70.3
Newark City | 8442 | 1892.22
North Arlington Boro | 533 | 123.09
North Bergen Twp | 1338 | 312.85
North Brunswick Twp | 2275 | 495.86
North Caldwell Twp | 204 | 47.14
North Haledon Boro | 51 | 11.74
North Hanover Twp | 2 | 0.48
North Plainfield Boro | 661 | 148.19
Nutley Town | 587 | 138.21
Oaklyn Boro | 292 | 61.66
Old Tappan Boro | 11 | 2.64
Oradell Boro | 103 | 22.85
Orange City | 615 | 146.05
Palisades Park Boro | 428 | 100.93
Palmyra Boro | 442 | 92.17
Paramus Boro | 795 | 180.15
Park Ridge Boro | 3 | 0.72
Passaic City | 1067 | 248.3
Paterson City | 3394 | 772.21
Paulsboro Boro | 6 | 1.24
Pemberton Twp | 136 | 28.28
Pennington Boro | 82 | 19.1
Pennsauken Twp | 3742 | 785.74
Perth Amboy City | 1669 | 362.1
Piscataway Twp | 3288 | 704
Plainfield City | 1785 | 395.9
Plainsboro Twp | 259 | 56.88
Princeton Boro | 55 | 12.52
Princeton Twp | 155 | 34.04
Prospect Park Boro | 113 | 25.33
Rahway City | 1550 | 347.91
Raritan Boro | 301 | 66
Ridgefield Boro | 375 | 87.62
Ridgefield Park Village | 400 | 94.59
Ridgewood Village | 151 | 34.14
River Edge Boro | 294 | 66.94
River Vale Twp | 13 | 2.87
Riverside Twp | 592 | 123.3
Riverton Boro | 119 | 25.64
Rochelle Park Twp | 270 | 61.95
Rocky Hill Boro | 18 | 3.94
Roseland Boro | 164 | 38.68
Roselle Boro | 711 | 157.18
Roselle Park Boro | 323 | 74.12
Runnemede Boro | 589 | 127.75
Rutherford Boro | 235 | 52.32
Saddle Brook Twp | 15 | 3.33
Saddle Brook Twp | 330 | 75.11
Saddle River Boro | 10 | 2.4
Scotch Plains Twp | 706 | 160.24
Secaucus Town | 1080 | 251.59
Somerdale Boro | 417 | 90.12
Somerville Boro | 776 | 169.56
South Bound Brook Boro | 217 | 47.74
South Brunswick Twp | 1601 | 349.01
South Brunswick Twp | 538 | 115.81
South Hackensack Twp | 234 | 54.48
South Orange Village Twp | 114 | 26.9
South Plainfield Boro | 2573 | 550.59
Southampton Twp | 870 | 182.26
Springfield Twp Bur | 528 | 110.3
Springfield Twp Uni | 32 | 7.29
Tavistock Boro | 1 | 0.22
Teaneck Twp | 757 | 174.28
Tenafly Boro | 338 | 77.18
Teterboro Boro | 183 | 42.87
Totowa Boro | 757 | 173.32
Trenton City | 5098 | 1110.17
Union City | 27 | 6.28
Union Twp Uni | 2334 | 515.6
Upper Freehold Twp | 82 | 17.57
Verona Boro | 194 | 46.24
Voorhees Twp | 352 | 76.83
Waldwick Boro | 191 | 42.69
Wallington Boro | 297 | 68.97
Wallington Boro | 5 | 1.16
Warren Twp | 60 | 12.8
Washington Twp Ber | 109 | 24.6
Washington Twp Glo | 39 | 8.4
Washington Twp Mer | 396 | 84.64
Watchung Boro | 357 | 79.38
Wayne Twp | 1418 | 324.6
Weehawken Twp | 3 | 0.72
West Caldwell Twp | 550 | 129.82
West Deptford Twp | 1 | 0.2
West Deptford Twp | 1865 | 400.33
West New York Town | 33 | 7.47
West Orange Twp | 1135 | 264.68
West Paterson Boro | 340 | 78.21
West Windsor Twp | 756 | 164.75
Westampton Twp | 480 | 101.03
Westfield Town | 1198 | 279.52
Westville Boro | 574 | 121.86
Westwood Boro | 228 | 50.5
Willingboro Twp | 841 | 174.11
Winfield Twp | 18 | 3.67
Woodbridge Twp | 6854 | 1444.37
Woodbury City | 1002 | 217.84
Woodbury Heights Boro | 280 | 60.78
Woodcliff Lake Boro | 69 | 16.26
Woodlynne Boro | 148 | 31.15
Wood-Ridge Boro | 387 | 90.7
Wyckoff Twp | 54 | 12.37
Grand Total: | 196129 | 43228.54

## Seg 2 - Aggregators by Muni
PSE&G Pole-Attached -- Count of Aggregators by Municipality - February 2025
Municipality | Count of Aggregators Installed through February 2025
Allentown Boro | 3
Audubon Boro | 7
Barrington Boro | 7
Bayonne City | 21
Belleville Twp | 15
Bellmawr Boro | 18
Bergenfield Boro | 8
Beverly City | 3
Bloomfield Twp | 18
Bogota Boro | 3
Bordentown City | 1
Bordentown Twp | 13
Bound Brook Boro | 6
Branchburg Twp | 1
Bridgewater Twp | 43
Brooklawn Boro | 6
Burlington City | 20
Burlington Twp | 19
Caldwell Boro | 4
Camden City | 62
Carlstadt Boro | 13
Carteret Boro | 19
Cedar Grove Twp | 8
Cherry Hill Twp | 64
Chesterfield Twp | 16
Cinnaminson Twp | 20
Clark Twp | 14
Cliffside Park Boro | 3
Clifton City | 42
Collingswood Boro | 10
Cranbury Twp | 20
Cranford Twp | 11
Delanco Twp | 3
Delran Twp | 11
Deptford Twp | 32
Dumont Boro | 6
Dunellen Boro | 4
East Brunswick Twp | 38
East Newark Boro | 6
East Orange City | 15
East Rutherford Boro | 6
Eastampton Twp | 8
Edgewater Boro | 10
Edgewater Park Twp | 6
Edison Twp | 83
Elizabeth City | 53
Elmwood Park Boro | 12
Emerson Boro | 7
Englewood City | 22
Englewood Cliffs Boro | 5
Essex Fells Twp | 2
Evesham Twp | 15
Ewing Twp | 35
Fair Lawn Boro | 17
Fairfield Twp Ess | 16
Fairview Boro | 5
Fanwood Boro | 5
Fieldsboro Boro | 1
Florence Twp | 12
Fort Lee Boro | 12
Franklin Twp Som | 67
Garfield City | 9
Garwood Boro | 3
Glen Rock Boro | 13
Gloucester City | 12
Gloucester Twp | 24
Green Brook Twp | 7
Guttenberg Town | 1
Hackensack City | 24
Haddon Heights Boro | 4
Haddon Twp | 13
Haddonfield Boro | 10
Hainesport Twp | 3
Haledon Boro | 1
Hamilton Twp Mer | 92
Harrison Town | 4
Hasbrouck Heights | 4
Haworth Boro | 2
Hawthorne Boro | 10
Highland Park Boro | 11
Hillsborough Twp | 39
Hillsdale Boro | 2
Hillside Twp | 10
Hi-Nella Boro | 1
Hoboken City | 12
Hohokus Boro | 3
Hopewell Boro | 4
Hopewell Twp Mer | 28
Irvington Town | 16
Jersey City | 89
Kearny Town | 15
Kenilworth Boro | 7
Lawnside Boro | 3
Lawrence Twp Mer | 36
Leonia Boro | 2
Linden City | 40
Little Falls Twp | 15
Little Ferry Boro | 7
Livingston Twp | 27
Lodi Boro | 11
Lumberton Twp | 14
Lyndhurst Twp | 12
Magnolia Boro | 5
Mansfield Twp Bur | 15
Manville Boro | 9
Maple Shade Twp | 12
Maplewood Twp | 7
Maywood Boro | 7
Medford Lakes Boro | 3
Medford Twp | 24
Merchantville Boro | 1
Metuchen Boro | 11
Middlesex Boro | 9
Midland Park Boro | 6
Millstone Boro | 1
Montclair Twp | 16
Montgomery Twp | 37
Moonachie Boro | 5
Moorestown Twp | 20
Mount Ephraim Boro | 4
Mount Holly Twp | 9
Mount Laurel Twp | 27
Mountainside Boro | 8
National Park Boro | 6
New Brunswick City | 26
New Milford Boro | 6
Newark City | 123
North Arlington Boro | 8
North Bergen Twp | 26
North Brunswick Twp | 25
North Caldwell Twp | 11
North Haledon Boro | 3
North Plainfield Boro | 8
Nutley Town | 8
Oaklyn Boro | 8
Old Tappan Boro | 1
Oradell Boro | 2
Orange City | 10
Palisades Park Boro | 5
Palmyra Boro | 7
Paramus Boro | 24
Passaic City | 22
Paterson City | 46
Pemberton Twp | 6
Pennington Boro | 3
Pennsauken Twp | 50
Perth Amboy City | 24
Piscataway Twp | 57
Plainfield City | 26
Plainsboro Twp | 10
Princeton Boro | 9
Princeton Twp | 15
Prospect Park Boro | 1
Rahway City | 17
Raritan Boro | 6
Ridgefield Boro | 3
Ridgefield Park Village | 6
Ridgewood Village | 10
River Edge Boro | 11
River Vale Twp | 1
Riverside Twp | 3
Riverton Boro | 3
Rochelle Park Twp | 5
Rocky Hill Boro | 4
Roseland Boro | 10
Roselle Boro | 10
Roselle Park Boro | 5
Runnemede Boro | 8
Rutherford Boro | 8
Saddle Brook Twp | 7
Saddle River Boro | 1
Scotch Plains Twp | 12
Secaucus Town | 17
Somerdale Boro | 6
Somerville Boro | 8
South Bound Brook Boro | 2
South Brunswick Twp | 48
South Hackensack Twp | 3
South Orange Village Twp | 5
South Plainfield Boro | 42
Southampton Twp | 23
Springfield Twp Bur | 14
Teaneck Twp | 17
Tenafly Boro | 12
Teterboro Boro | 2
Totowa Boro | 11
Trenton City | 56
Union City | 2
Union Twp Uni | 34
Upper Freehold Twp | 2
Verona Boro | 3
Voorhees Twp | 7
Waldwick Boro | 10
Wallington Boro | 2
Warren Twp | 5
Washington Twp Ber | 6
Washington Twp Glo | 2
Washington Twp Mer | 3
Watchung Boro | 14
Wayne Twp | 52
West Caldwell Twp | 9
West Deptford Twp | 24
West New York Town | 3
West Orange Twp | 27
West Paterson Boro | 9
West Windsor Twp | 22
Westampton Twp | 9
Westfield Town | 27
Westville Boro | 4
Westwood Boro | 5
Willingboro Twp | 18
Woodbridge Twp | 90
Woodbury City | 16
Woodbury Heights Boro | 1
Woodcliff Lake Boro | 5
Woodlynne Boro | 2
Wood-Ridge Boro | 4
Wyckoff Twp | 5
Grand Totals: | 3302